## Sheet1
REFRIGERATION UNIT STYRENE PARK OFFSITE
|  | Vendor Print Index & Schedule (VPIS) |  |  |  | CLIENT | VENDOR
PO No.:
VPIS Rev: 00 |  | MR No.: | PR No.: | [11 empty] | REV 00 | [6 empty] | REV 01 | [6 empty] | REV 02 | [6 empty] | REV 03 | [6 empty] | REV 04 | [6 empty] | REV 05 | [6 empty] | REV 06
Item No. | Document Number | Document Title | Type | Rev | Planned Issue Date | HSE hand | Last Rev. | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK
GENERAL
1 | EI027-HSE-VD – GE– SCH– 001- XX | Project Schedule |  | 0 |  | CLIENT | 0 | 20 | 2024-04-30 | [5 empty] | 20 | 2024-04-30
2 | EI027-HSE-VD – GE– LST– 002- XX | Vendor Document & Index Schedule (VDIS) |  | 0 |  | CLIENT | 0 | 1 | 2023-09-04 | APPROVED |  |  |  |  | 1 | 2023-09-04 | APPROVED
3 | EI027-HSE-VD – GE– LST– 003- XX | Final data book Index | [61 empty] | STATUS LIST
4 | EI027-HSE-VD – GE– FDB– 004- XX | Final data book | [61 empty] | COMMENTED
5 | EI027-HSE-VD – GE– PRO– 005- XX | Packing, Marking & Shipping Procedure | [61 empty] | APPROVED
6 | EI027-HSE-VD – GE– LST– 006- XX | Sub-Vendor List |  | 1 |  | HSE | 1 | 12 | 2024-04-07 | APPROVED | 2024-04-15 |  |  |  | 8 | 2024-02-18 | COMMENTED | 2024-02-19 | 2024-04-07 |  |  | 12 | 2024-04-07 | APPROVED | 2024-04-15 | [38 empty] | NO COMMENT
7 | EI027-HSE-VD – GE– LST– 007- XX | Spare Part List for Commissioning & Start-up and Two Years Operation | [61 empty] | AN
8 | EI027-HSE-VD – GE– LST– 008- XX | Special Tools List | [61 empty] | COMMENTED
PROCESS
9 | EI027-HSE-VD – PR– PFD– 001- XX | Process Flow Diagram (PFD) |  | 1 |  | CLIENT | 1 | 28 | 2024-06-15 | [5 empty] | 19 | 2024-04-28 | AN | 2024-05-20 |  |  |  | 28 | 2024-06-15
10 | EI027-HSE-VD – PR– PID– 002- XX | Piping And Instrumentation Diagram (P&ID)
11 | EI027-HSE-VD – PR– LST– 003- XX | Utility Consumption List including Electrical Load List
12 | EI027-HSE-VD – PR– LST– 004- XX | Lubricant List/Grease List
CIVIL
13 | EI027-HSE-VD – CI– DWG– 001- XX | Skid Foundation Plan
MECHANICAL
14 | EI027-HSE-VD – ME– DSH– 001- XX | Package / Compressor Data Sheet |  | 2 |  | HSE | 2 | 21 | 2024-05-07 | APPROVED | 2024-05-20 |  |  |  | 2 | 2023-09-09 | COMMENTED | MOM |  |  |  | 7 | 2024-02-05 | COMMENTED | 2024-02-12 | 2024-02-18 | 2024-03-27 | 2024-04-07 | 21 | 2024-05-07 | APPROVED | 2024-05-20
15 | EI027-HSE-VD – ME– DWG– 002- XX | Compressor Package Outline Drawing |  | 1 |  | CLIENT | 1 | 27 | 2024-06-12 | [5 empty] | 6 | 2024-02-03 | COMMENTED | 2024-02-19 | 2024-06-12 |  |  | 27 | 2024-06-12
16 | EI027-HSE-VD – ME– DWG– 003- XX | Oil Heater Data Sheet and Drawing
17 | EI027-HSE-VD – ME– DSH– 004- XX | Condenser Data Sheet |  | 2 |  | HSE | 2 | 22 | 2024-05-07 | APPROVED | 2024-05-20 |  |  |  | 10 | 2024-03-16 | COMMENTED | 2024-03-27 | 2024-04-08 |  |  | 15 | 2024-04-09 | APPROVED | 2024-04-20 |  |  |  | 22 | 2024-05-07 | APPROVED | 2024-05-20
18 | EI027-HSE-VD – ME– DWG– 005- XX | Condenser Outline Drawing
19 | EI027-HSE-VD – ME– CAL– 006- XX | Mechanical calculation for Condenser |  | 0 |  | CLIENT | 0 | 26 | 2024-06-11 | [5 empty] | 26 | 2024-06-11
20 | EI027-HSE-VD – ME– DSH– 007- XX | Chiller (Evaporator) Data Sheet |  | 2 |  | HSE | 2 | 17 | 2024-05-07 | APPROVED | 2024-05-20 |  |  |  | 9 | 2024-02-21 | COMMENTED | 2024-03-05 | 2024-03-06 | 2024-03-27 | 2024-04-08 | 14 | 2024-04-08 | COMMENTED | 2024-04-14 | 2024-04-20 |  |  | 17 | 2024-05-07 | APPROVED | 2024-05-20
21 | EI027-HSE-VD – ME– DWG– 008- XX | Chiller (Evaporator) Outline Drawing |  | 0 |  | CLIENT | 0 | 24 | 2024-05-20 | [5 empty] | 24 | 2024-05-20
22 | EI027-HSE-VD – ME– CAL– 009- XX | Chiller (Evaporator) Mechanical calculation |  | 1 |  | CLIENT | 1 | 25 | 2024-05-25 | [5 empty] | 18 | 2024-04-20 | AN |  |  |  |  | 25 | 2024-05-25
23 | EI027-HSE-VD – ME– DSH– 010- XX | Filter Dryer Data Sheet
PIPPING
24 | EI027-HSE-VD – PI– DWG– 001- XX | General Arrangement Drawing |  | 0 |  | HSE | 0 | 16 | 2024-04-18 | APPROVED | 2024-05-20 |  |  |  | 16 | 2024-04-18 | APPROVED | 2024-05-20
25 | EI027-HSE-VD – PI– MOD– 002- XX | 3D Model
QUALITY CONTROL
26 | EI027-HSE-VD – QC– ITP– 001- XX | Inspection And Test (ITP) |  | 2 |  | CLIENT | 2 | 13 | 2024-04-07 | [5 empty] | 3 | 2023-09-17 | COMMENTED | 2023-09-18 |  |  |  | 4 | 2023-09-18 | COMMENTED | 2023-12-31 |  |  |  | 13 | 2024-04-07
27 | EI027-HSE-VD – QC– PRO– 002- XX | Painting Procedure
28 | EI027-HSE-VD – QC– PRO– 003- XX | Compressor Test Procedure |  | 0 |  | CLIENT | 0 | 23 | 2024-05-15 | [5 empty] | 23 | 2024-05-15
29 | EI027-HSE-VD – QC– PRO– 004- XX | Test Procedure For Air Condenser and Chiller
30 | EI027-HSE-VD – QC– PRO– 005- XX | Weld book WPS/PQR/Weld Map For Air Condenser and Chiller
INSTRUMENTATION AND CONTROL SYSTEM
31 | EI027-HSE-VD – IN– DIG– 001- XX | Cause & Effect Diagram
32 | EI027-HSE-VD – IN– DSH– 002- XX | Control Valve Data Sheet
33 | EI027-HSE-VD – IN– DSH– 003- XX | Instrument Data Sheet
34 | EI027-HSE-VD – IN– DIG– 004- XX | Local Panel and Junction Box Wiring Diagrams
35 | EI027-HSE-VD – IN– LST– 005- XX | I/O-list
36 | EI027-HSE-VD – IN– DSH–006- XX | ON/OFF-Solenoid Valve Data Sheet
37 | EI027-HSE-VD – IN– DSH–007- XX | Safety / Relief Valve Data Sheet
38 | EI027-HSE-VD – IN– DIG–008- XX | PLC Layout Drawing
ELECTRICAL
39 | EI027-HSE-VD – EL– DSH– 001- XX | Compressor Motor Data Sheet & Drawing |  | 0 |  | CLIENT | 0 | 11 | 2024-03-24 | APPROVED | 2024-04-21 | 2024-05-05 |  |  | 11 | 2024-03-24 | APPROVED | 2024-04-21 | 2024-05-05
40 | EI027-HSE-VD – EL– DSH– 002- XX | Oil pump Motor Datasheet & Drawing |  | 0 |  | CLIENT | 0 | 11 | 2024-03-24 | APPROVED | 2024-04-21 | 2024-05-05 |  |  | 11 | 2024-03-24 | APPROVED | 2024-04-21 | 2024-05-05
41
42
43
44
45
46
47
48
49
50
51
52
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
Formulas:
HSE TR Date = IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],"")))))))
CLIENT = IF(OR([STATUS]="CODE 1"),"",IF(AND([VENDOR]<>"",[CLIENT CM Date]<>""),(TODAY()-[CLIENT CM Date]-7),IF([VENDOR]<>"","","")))