## Cover
STYRENE PARK OFFSITE
Work Beakdown Structure for Ru0001A / B-D-02
00 | 15-April-2025 | IFA | F.M | M.Y | S.Dr
Rev. | Issue Date | Purpose of Issue | Prepared | Checked | Approved | Contractor’s Approval | PEDEC Approval
Vendor
Document No.: EI027-ASP-VD-ME-SCH-016
Toase-ehe Park Sanati Gohar Ofogh
Petrochemical Co.
CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Work Beakdown Structure for Ru0001A / B-D-02
Class: 1
Rev.: 00
Status: IFA

## Rev. Sheet
Page | Revision |  |  |  |  | Page | Revision |  |  |  |  | Page | Revision
| D00 | D01 | D02 | D03 | D04 |  | D00 | D01 | D02 | D03 | D04 |  | D00 | D01 | D02 | D03 | D04
1 | X
2 | X
3 | X
4 | X
5 | X
Document No.: EI027-ASP-VD-ME-SCH-016
Toase-ehe Park Sanati Gohar Ofogh
Petrochemical Co.
CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Work Beakdown Structure for Ru0001A / B-D-02
Class: 1
Rev.: 00
Status: IFA

## WBS
WBS Code | Description | Total Weight Factor | Level Weight Factor | Weight Factor Sub-Level
|  |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | Level 7
1 | Contract Title | 100% | 100% | 100%
1.2 | Vessels 1&2 | 100% | 5% |  | 5%
1.2.1 | Engineering | 5% | 5% |  |  | 5%
1.2.1.1 | Engineering & Designing | 5% | 100% |  |  |  | 100%
1.2.2 | Supply of Raw Material | 30% | 30% |  |  | 30%
1.2.2.1 | Plate & U-Bult | 12% | 40% |  |  |  | 40%
1.2.2.2 | Paint Material | 18% | 60% |  |  |  | 60%
1.2.3 | CONSTRUCTION | 42% | 42% |  |  | 42%
1.2.3.1 | Mechanical | 27% | 65% |  |  |  | 27%
1.2.3.1.1 | Elliptical Head 1 & 2 | 9.327% | 40% |  |  |  |  | 40%
1.2.3.1.1.1 | Cutting | 1.473% | 16% | [5 empty] | 16%
1.2.3.1.1.2 | Grinding | 0.9818% | 10% | [5 empty] | 10%
1.2.3.1.1.3 | Beveling | 0.9818% | 10% | [5 empty] | 10%
1.2.3.1.1.4 | Fitup | 0.9818% | 10% | [5 empty] | 10%
1.2.3.1.1.5 | Head manufacturing | 4.909% | 54% | [5 empty] | 54%
1.2.3.1.2 | Shell | 7.855% | 17% |  |  |  |  | 17%
1.2.3.1.2.1 | Shell Plate Course1 | 3.927% | 50% | [5 empty] | 50%
1.2.3.1.2.1.1 | Cutting | 0.4909% | 12.5% | [6 empty] | 12.5%
1.2.3.1.2.1.2 | Grinding | 0.4909% | 12.5% | [6 empty] | 12.5%
1.2.3.1.2.1.3 | Beveling | 0.4909% | 12.5% | [6 empty] | 12.5%
1.2.3.1.2.1.4 | Rolling | 1.473% | 37.5% | [6 empty] | 37.5%
1.2.3.1.2.1.5 | Welding | 0.9818% | 25% | [6 empty] | 25%
1.2.3.1.2.2 | Shell Plate Course2 | 3.927% | 50% | [5 empty] | 50%
1.2.3.1.2.2.1 | Cutting | 0.4909% | 12.5% | [6 empty] | 12.5%
1.2.3.1.2.2.2 | Grinding | 0.4909% | 12.5% | [6 empty] | 12.5%
1.2.3.1.2.2.3 | Beveling | 0.4909% | 12.5% | [6 empty] | 12.5%
1.2.3.1.2.2.4 | Rolling | 1.473% | 37.5% | [6 empty] | 37.5%
1.2.3.1.2.2.5 | Welding | 0.9818% | 25% | [6 empty] | 25%
1.2.3.1.3 | Welding Shell to Shell & Shell to Head | 4.418% | 19% |  |  |  |  | 19%
1.2.3.1.3.1 | Fitup of Shell Course 1 to Shell Course 2 | 1.473% | 32% | [5 empty] | 32%
1.2.3.1.3.1.1 | Fitup | 0.4909% | 34% | [6 empty] | 34%
1.2.3.1.3.1.2 | Welding | 0.9818% | 66% | [6 empty] | 66%
1.2.3.1.3.2 | Fitup of Shell Course 1 to Head 2 | 1.473% | 34% | [5 empty] | 34%
1.2.3.1.3.2.1 | Fitup | 0.4909% | 34% | [6 empty] | 34%
1.2.3.1.3.2.2 | Welding | 0.9818% | 66% | [6 empty] | 66%
1.2.3.1.3.3 | Fitup of Shell Course 2 to Head 2 | 1.473% | 34% | [5 empty] | 34%
1.2.3.1.3.3.1 | Fitup | 0.4909% | 34% | [6 empty] | 34%
1.2.3.1.3.3.2 | Welding | 0.9818% | 66% | [6 empty] | 66%
1.2.3.1.4 | Saddle | 1.964% | 9% |  |  |  |  | 9%
1.2.3.1.4.1 | Cutting | 0.4909% | 25% | [5 empty] | 25%
1.2.3.1.4.2 | Fitup | 0.4909% | 25% | [5 empty] | 25%
1.2.3.1.4.3 | Welding | 0.9818% | 50% | [5 empty] | 50%
1.2.3.1.3.5 | Nozzle | 3.436% | 15% |  |  |  |  | 15%
1.2.3.1.3.5.1 | Cutting | 0.4909% | 14% | [5 empty] | 14%
1.2.3.1.3.5.2 | Beveling | 0.4909% | 14% | [5 empty] | 14%
1.2.3.1.3.5.3 | Fitup | 0.9818% | 29% | [5 empty] | 29%
1.2.3.1.3.5.4 | Welding | 1.473% | 43% | [5 empty] | 43%
1.2.3.2 | Painting | 15% | 15% |  |  |  | 15%
1.2.3.2.1 | External Painting | 15% | 35% |  |  |  |  | 35%
1.2.3.2.1.1 | Blasting | 3.75% | 25% | [5 empty] | 25%
1.2.3.2.1.2 | Painting | 11.25% | 75% | [5 empty] | 75%
1.2.4 | PRE COMMISSIONING & COMMISSIONING | 18% | 18% |  |  | 18%
1.2.4.1 | Pre Commissioning | 12% | 12% |  |  |  | 66%
1.2.4.1.1 | Hydrostatic test | 4% | 34% |  |  |  |  | 34%
1.2.4.1.2 | N2 Filling Procedure | 8% | 66% |  |  |  |  | 66%
1.2.4.2 | COMMISSIONING | 6% | 6% |  |  |  | 34%
1.2.4.2.1 | Tank Delivery to client | 6% | 100% |  |  |  |  | 100%
1.2.5 | Final Data Book | 5% | 5% |  |  | 5%
1.2.5.1 | Final Data Book | 5% | 100% |  |  |  | 100%
Document No.: EI027-ASP-VD-ME-SCH-016
Toase-ehe Park Sanati Gohar Ofogh
Petrochemical Co.
CONCEPTUAL, BASIC and DETAIL DESIGN ENGINEERING OF STYRENE PARK OFFSITE
Work Beakdown Structure for Ru0001A / B-D-02
Class: 1
Rev.: 00
Status: IFA