| Attendees: (*: Part Time Attendance) |  |  |  |
| --- | --- | --- | --- |
| Company/Discipline | Name | Title | Signature |
| Client: Padjam CO / Gohar Ofogh | Mr. Bakhtiari | Project Manager – Padjam CO |  |
|  | Mr. KHavarinia | Engineering Manager- Padjam CO |  |
|  | Mr. Ahangaran | Electrical Instrument Manager – Padjam CO |  |
|  | Mr. Javid | Electrical Instrument Manager – Gohar Ofogh |  |
| Consulter: |  |  |  |
| Purchaser: Petroelectric Energy Development CO (PEDCo.) | Mr. Mehran taebi | Project Manager |  |
|  | Mr.M. Namazi | Engineering Manager |  |
|  | Mr. Fr.Yari | Procurement Manager |  |
|  | - | - |  |
|  | - | - |  |
|  | - | - |  |
|  | - | - |  |
| Delta GmbH | Mr. A.Malekinia | MD1 |  |
|  | Mr. H. Habibpour | MD2 |  |
|  | Mr. M. Osta | Engineering Manager |  |
|  | Mr. F. Shoarian | Project Manager |  |
|  | - | - |  |
|  | - | - |  |

| 1. COORDINATION: 1.1. Contact Information |  |  |  |  |
| --- | --- | --- | --- | --- |
| A) Petro Electric Energy Development Representatives (Purchaser): |  |  |  |  |
| Position | Name | Ext. No.: | Fax No.: | Email: |
| Project Manager | Mr. Bakhtiari | 8184 |  | M.bakhtiari@pjpc.ir |
| Engineering Manager | Mr. KHavarinia |  |  |  |
| Electrical Instrument Manager – Padjam CO | Mr. Ahangaran |  |  | h.ahangaran@pjpc.ir |
| Electrical Instrument Manager – Gohar Ofogh | Mr. Javid | 207 |  | Javid@gopc.ir |
| Project Manager | Mr. Mehran taebi | 416 |  | Taebi.m@petroelectric.ir |
| Engineering Manager | Mr.M. Namazi | 412 |  | Namazi.m@petroelectric.ir |
| Procurement Manager | Mr. Fr.Yari | 499 |  | Yari.f@ petroelectric.ir |
| Contract Manager | Mr. Ebrahim Afkhami | 402 |  | Afkhami.e@petroelectric.ir |
| QC Manager | Mr. Saeid Ghodrati |  |  | Saeid_ghodrati2000@yahoo.com |
| Document Controller Center | Mr. Saman Firoozabadi | 419 |  | firoozabadi.s@petroelectric.ir |
| Planning manager | Mr. Farhad Jalali | 150 |  | Jalali.f@petroelectric.ir |
| B) Vendor Representatives: |  |  |  |  |
| Position | Name | Tel. No.: | Ext No.: | Email: |
| MD1 | Mr. A.Malekinia | 0912-2493533 |  | bd@delta-gmbh.eu |
| MD2 | Mr. H. Habibpour | 0912-7230269 |  | habibpour@delta-gmbh.eu |
| Engineering Manager | Mr. M. Osta | 0912-6442806 |  | sourcing@delta-gmbh.eu |
| Project Manager | Mr. F. Shoarian | 0912-6273626 |  | planning@delta-gmbh.eu |
|  | - | - | - | - |
| 1.2) Correspondence: 1.2.1) Correspondence procedure: All technical & un-priced correspondences shall be done through Exchange Server (Email). |  |  |  |  |
| 1.2.2) From Vendor to Gohar Ofogh Co/Petro Electric Energy Development Co (Transmittal / e-mail): - All technical documents (including V.P.I.S and none-commercial issues) shall be sent to: Name: Mr. Javid E-mail TO: Javid@gopc.ir CC : Namazi.m@petroelectric.ir; Yari.f@ petroelectric.ir; h.ahangaran@pjpc.ir; engproject.gopc@gmail.com; Tel No. : 021-88373529 Extension :412 - Commercial matters shall be sent to below email addresses. Name: Mr. Fereidoun Yari E-mail : Yari.f@petroelectric.ir CC : Afkhami.e@petroelectric.ir Tel No. : 021-88373529 Extension :499 - All Inspection and QC matters shall be sent to below email addresses. Name: Saeeid Ghodrati E-mail : Ghodrati.S@petroelectric.ir; Saeid_ghodrati2000@yahoo.com CC : M.bakhtiari@pjpc.ir ; Taebi.m@petroelectric.ir ; Javid@gopc.ir ; Yari.f@petroelectric.ir; D.kianersi@jpcomplex.com; tavana@gopc.info; Tel No. : 021-88373529 Extension :101 Postal address: NO 120, Dadman Blv, Shahrak-e-Gharb, Tehran, Iran. |  |  |  |  |
| 1.2.2) Type of correspondence/ documents (Soft Copy): - Vendor to issue “Vendor Print Index and Schedule” (V.P.I.S.) according to the list of documents indicated in the relevant Material Requisition three days before K.O.M by email. No Document / Drawing will be reviewed before V.P.I.S. submission. - All E-files shall be provided in PDF files. - All Documents / Drawings shall be presented in English. - The sequence of document issue shall be as per approved VPIS and document will be rejected if vendor doesn’t follow the sequence. |  |  |  |  |
| 2. PLANNING: 2.1) Updating Time schedule Detail Time Schedule must be prepared as clause 2.2 and be updated Bi-Weekly, by setting STATUS Date (in MSP) on Cut-off date, inserting Actual START/FINISH Dates, defining Remaining Duration for in progress Activities and finally rescheduling Project by applying “rescheduling uncompleted work to Start after” option in MSP. Also Vendor shall submit the Native and PDF files of updated time Schedule as attachment of Monthly Progress Report. 2.2) Monthly Progress Reports (MPR) : Vendor shall prepare and issue Bi-Weekly Progress Report in JV format which is available through |  |  |  |  |
| 3. EXPEDITING: 3.1) Based on Approved ITP |  |  |  |  |
| 3.2) List of sub- vendors: Sub-vendor list with related origin country issued as attached. |  |  |  |  |
| 3.3) Fabrication and delivery location: 3.4.1) As per PO, Fabrication location will be at manufacture shop. 3.4.2) As per PO, Delivery Term: As per contract. |  |  |  |  |
| 4. ENGINEERING: 4.1) Documents and drawings (Review / Comment / Approval): 4.1.1) Emergency Diesel Gen, data sheet to be filled in and also signed and stamped by esteemed vendor in detail. (Data sheet Doc. No. SS1-DG-01 & SS2-DG-01, Rev.01) 4.1.2) L.V Single Line Diagram for S.S#01 to be signed and stamped by esteemed vendor in detail. (Dwg. No. EI027-000-ED-EL-SLD-004, Rev04) 4.1.3) L.V Single Line Diagram for S.S#02 to be signed and stamped by esteemed vendor in detail. (Dwg. No. EI027-000-ED-EL-SLD-005, Rev03) 4.1.4) Gen. Set Control system shall be interface with PDCS Control system such as on/off status, Test/Service position, Fault/Unavailable status, Open Command, Close command, … by Mod-Bus Serial Link, RS485 Physical layer. (I/O List for PDCS System EI027-000-EL=LST-1001, Rev.01) 4.1.5) Derating Factors curves shall be considered Acc. to project site condition data sheet by esteemed vendor. (Site and Design condition for Offsite Area, EI027-000-ED-PR-SPC-002, Rev.02) 4.1.6) Each Vendor document shall be reviewed and all commented during 5 work days by GOPC. 4.1.7) each document to be revised by Vendor shall have revision mark and cloud mark in all required parts. Otherwise it will not be reviewed and Vendor would be responsible for any possible caused problem. 4.1.8) vendor shall submit progress report and time schedule during manufacturing procedure time in each month. - INSPECTION Procedure: 4.1.9) Inspection & Test Plan (ITP) shall be submitted on 03. August.2023 by Vendor in PJPC Project format. The PIM will be held on 05. Aug.2023 at Petro Electric Co. |  |  |  |  |
| 4.2) Vendor scope of work: As per PO and its attachments |  |  |  |  |
| 4.3) Technical comments and clarifications: 4.3.1) Deviations is issued by vendor as attached. |  |  |  |  |
| 4.4) Documents & drawings templates / title block (ACAD, Word, Excel…): |  |  |  |  |
| 4.5) Previous tech. agreements (Validity / Conflicts): All of the previous agreements between Petro Electric Energy Development and VENDOR are valid. |  |  |  |  |
| 4.6) Vendor Final Data book: Vendor Final Data Book shall be submitted as per “INSTRUCTION FOR VENDOR DOCUMENTATION and PROCEDURE” and Also VPIS Index which shall be issued and sent with hard copies of documents. |  |  |  |  |
| Attachments: - WBS, Planning report, title block format and numbering procedure are attached as compact disc. |  |  |  |  |