## active carbon
|  | FILTER PACKAGE STYRENE PARK OFFSITE |  |  |  | Color Legend:
|  | Vendor Print Index & Schedule (VPIS) |  |  |  | Approved | CLIENT | VENDOR
PO No.:
VPIS Rev: 00 |  | MR No.: | PR No.: |  |  | LAST STATUS | [9 empty] | REV 00 | [6 empty] | REV 01 | [6 empty] | REV 02 | [6 empty] | REV 03 | [6 empty] | REV 04 | [6 empty] | REV 05 | [6 empty] | REV 06
Item No. | Document Number | Document Title | Type | Rev | Planned Issue Date | Client hand | HSE hand | Last Rev. | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | Weight Factor % |  | TO | TO | CC | CC | DONT TOUCH
1 | EI027-ENR-VD-GE-LST-001 | Vendor Print Index and Schedule (VPIS) for Active Carbon Filter |  | 1 |  |  |  | 1 | 5 | 2024-03-11 | APPROVED | 2024-03-13 |  |  |  | 1 | 2024-02-14 | [5 empty] | 5 | 2024-03-11 | APPROVED | 2024-03-13 | [39 empty] | 100% | [5 empty] | FALSE | FALSE
2 | EI027-ENR-VD-GE-LST-002 | Sub Vendor List for Active Carbon Filter |  | 0 |  |  |  | 0 | 34 | 2024-06-19 | [5 empty] | 34 | 2024-06-19 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
3 | EI027-ENR-VD-GE-SCH-003 | Project Time Schedule for Active Carbon Filter |  | 1 |  |  |  | 1 | 4 | 2024-03-11 | APPROVED | 2024-03-13 |  |  |  | 1 | 2024-02-21 | [5 empty] | 4 | 2024-03-11 | APPROVED | 2024-03-13 | [39 empty] | 90% | [5 empty] | FALSE | FALSE
4 | EI027-ENR-VD-GE-LST-004 | Commissioning Spare Part List for Active Carbon Filter | [63 empty] | 90% |  |  |  |  | STATUS LIST | FALSE | FALSE
5 | EI027-ENR-VD-GE-LST-005 | Two Years Operation Spare Parts List for Active Carbon Filter | [63 empty] | 90% |  |  |  |  | COMMENTED | FALSE | FALSE
6 | EI027-ENR-VD-GE-LST-006 | Final Book Index for Active Carbon Filter | [63 empty] | 90% |  |  |  |  | APPROVED | FALSE | FALSE
7 | EI027-ENR-VD-GE-LST-007 | Final Book for Active Carbon Filter | [63 empty] | 90% |  |  |  |  | NO COMMENT | FALSE | FALSE
8 | EI027-ENR-VD-QC-ITP-001 | Inspection And Test Plan for Active Carbon Filter |  | 2 |  |  |  | 2 | N | 2024-03-03 | APPROVED | 2024-03-03 |  |  |  | 1 | 2024-02-20 | [5 empty] | 1 | 2024-02-26 | [5 empty] | N | 2024-03-03 | APPROVED | 2024-03-03 | [32 empty] | 90% | [5 empty] | FALSE | FALSE
9 | EI027-ENR-VD-QC-PRO-002 | Welding Procedure Specification & Qualification Records for Active carbon Filter |  | 0 |  |  |  | 0 | 6 | 2024-03-18 | [5 empty] | 6 | 2024-03-18 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
10 | EI027-ENR-VD-QC-PRO-003 | Preservation , Packaging, And Shipping Procedure for Active Carbon Filter |  | 0 |  |  |  | 0 | 18 | 2024-04-15 | [5 empty] | 18 | 2024-04-15 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
11 | EI027-ENR-VD-QC-PRO-004 | Test Procedures for Active Carbon Filter |  | 0 |  |  |  | 0 | 28 | 2024-06-11 | [5 empty] | 28 | 2024-06-11 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
12 | EI027-ENR-VD-PR-PRO-001 | Installation, Operating and Maintenance Manual for Active Carbon Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
13 | EI027-ENR-VD-PR-PFD-002 | PFD for Active Carbon Filter |  | 1 |  |  |  | 1 | 19 | 2024-04-16 | APPROVED | 2024-05-08 | 2024-05-20 |  |  | 1 | 2024-02-21 | COMMENTED | 2024-04-03 | 2024-05-20 |  |  | 19 | 2024-04-16 | APPROVED | 2024-05-08 | 2024-05-20 | [38 empty] | 90% | [5 empty] | FALSE | FALSE
14 | EI027-ENR-VD-PR-PID-003 | P&ID for Active Carbon Filter |  | 3 |  |  |  | 3 | 22 | 2024-04-24 | APPROVED |  |  |  |  | 1 | 2024-02-21 | COMMENTED | 2024-03-03 | 2024-04-08 |  |  | 10 | 2024-04-08 | APPROVED | 2024-04-14 |  |  |  | 15 | 2024-04-14 | COMMENTED | 2024-04-20 | 2024-04-24 |  |  | 22 | 2024-04-24 | APPROVED | [26 empty] | 90% | [5 empty] | FALSE | FALSE
15 | EI027-ENR-VD-PR-DCR-004 | Process Description for Active Carbon Filter |  | 1 |  |  |  | 1 | 21 | 2024-04-22 | APPROVED |  |  |  |  | 1 | 2024-02-21 | COMMENTED | 2024-03-03 | 2024-04-22 |  |  | 21 | 2024-04-22 | APPROVED | [40 empty] | 90% | [5 empty] | FALSE | FALSE
16 | EI027-ENR-VD-ME-DSH-001 | Equipment Data Sheet-Active Carbon Filter |  | 2 |  |  |  | 2 | 13 | 2024-04-14 | APPROVED | 2024-04-23 | 2024-05-20 |  |  | 1 | 2024-02-21 | COMMENTED | 2024-04-03 | 2024-04-08 |  |  | 7 | 2024-04-08 | APPROVED | 2024-04-14 |  |  |  | 13 | 2024-04-14 | APPROVED | 2024-04-23 | 2024-05-20 | [31 empty] | 90% | [5 empty] | FALSE | FALSE
17 | EI027-ENR-VD-ME-CAL-003 | Strength Calculation-Active Carbon Filter |  | 1 |  |  |  | 1 | 8 | 2024-05-26 | APPROVED |  |  |  | 8-apr-24 replaced | 1 | 2024-02-27 | COMMENTED | 2024-04-03 | 2024-04-08 |  |  | 8 | 2024-05-26 | APPROVED |  |  |  | 8-apr-24 replaced | [36 empty] | 90% | [5 empty] | FALSE | FALSE
18 | EI027-ENR-VD-ME-DWG-005 | General Arrangement Drawing-Active Carbon Filter |  | 1 |  |  |  | 1 | 16 | 2024-05-26 | APPROVED |  |  |  | 15-apr-24 replaced | 2 | 2024-03-05 | COMMENTED | 2024-03-16 | 2024-04-15 |  |  | 16 | 2024-05-26 | APPROVED |  |  |  | 15-apr-24 replaced | [36 empty] | 90% | [5 empty] | FALSE | FALSE
19 | EI027-ENR-VD-ME-DWG-007 | Name Plate Drawing for Active Carbon Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
20 | EI027-ENR-VD-ME-DWG-008 | Ladder & Platform Drawing for Active Carbon Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
21 | EI027-ENR-VD-PI-DWG-001 | GAD For Package for Active Carbon Filter |  | 0 |  |  |  | 0 | 27 | 2024-05-26 | APPROVED |  |  |  |  | 27 | 2024-05-26 | APPROVED | [47 empty] | 90% | [5 empty] | FALSE | FALSE
22 | EI027-ENR-VD-PI-MTO-002 | MTO for Piping for Active Carbon Filter |  | 0 |  |  |  | 0 | 32 | 2024-06-19 | [5 empty] | 32 | 2024-06-19 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
23 | EI027-ENR-VD-IN-LST-001 | Instrument List for Active Carbon Filter |  | 1 |  |  |  | 1 | 25 | 2024-04-30 | APPROVED |  |  |  | FI 19-jun-24 | 12 | 2024-04-13 | COMMENTED | 2024-04-23 | 2024-04-30 |  |  | 25 | 2024-04-30 | APPROVED |  |  |  | FI 19-jun-24 | [36 empty] | 90% | [5 empty] | FALSE | FALSE
24 | EI027-ENR-VD-IN-LST-002 | I\O List for Active Carbon Filter |  | 0 |  |  |  | 0 | 24 | 2024-04-29 | APPROVED |  |  |  | FI 19-jun-24 | 24 | 2024-04-29 | APPROVED |  |  |  | FI 19-jun-24 | [43 empty] | 90% | [5 empty] | FALSE | FALSE
25 | EI027-ENR-VD-IN-DSH-003 | Instrument Data Sheet for Active Carbon Filter |  | 0 |  |  |  | 0 | 20 | 2024-04-22 | APPROVED |  |  |  | FI 19-jun-24 | 20 | 2024-04-22 | APPROVED |  |  |  | FI 19-jun-24 | [43 empty] | 90% | [5 empty] | FALSE | FALSE
26 | EI027-ENR-VD-IN-DW G-004 | Hook Up Drawing for Active Carbon Filter |  | 0 |  |  |  | 0 | 23 | 2024-04-28 | APPROVED |  |  |  | FI 19-jun-24 | 23 | 2024-04-28 | APPROVED |  |  |  | FI 19-jun-24 | [43 empty] | 90% | [5 empty] | FALSE | FALSE
27 | EI027-ENR-VD-IN-LST-005 | Instrument Cable List for Active Carbon Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
28 | EI027-ENR-VD-IN-DW G-006 | Junction Boxes Wiring Diagrams And Outline Drawing for Active carbon Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
29 | EI027-ENR-VD-CL-DW G-001 | Foundation Plans With Static/Dynamic Loads, And Bolts Detail for active carbon Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
30 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
31 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
32 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
33 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
34 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
35 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
36 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
37 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
38 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
39 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
40 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
41 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
42 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
43 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
44 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
45 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
46 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
47 | [71 empty] | FALSE | FALSE
48 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
49 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
50 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
51 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
52 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
52 | [65 empty] | 90%
53 | [65 empty] | 90%
54 | [65 empty] | 90%
55 | [65 empty] | 90%
56 | [65 empty] | 90%
57 | [65 empty] | 90%
58 | [65 empty] | 90%
59 | [65 empty] | 90%
60 | [65 empty] | 90%
61 | [65 empty] | 90%
62 | [65 empty] | 90%
63 | [65 empty] | 90%
64 | [65 empty] | 90%
65 | [65 empty] | 90%
66 | [65 empty] | 90%
67 | [65 empty] | 90%
68 | [65 empty] | 90%
69 | [65 empty] | 90%
70 | [65 empty] | 90%
71 | [65 empty] | 90%
72 | [65 empty] | 90%
73 | [65 empty] | 90%
74 | [65 empty] | 90%
75 | [65 empty] | 90%
76 | [65 empty] | 90%
77 | [65 empty] | 90%
78 | [65 empty] | 90%
79 | [65 empty] | 90%
80 | [65 empty] | 90%
81 | [65 empty] | 90%
82 | [65 empty] | 90%
83 | [65 empty] | 90%
84 | [65 empty] | 90%
85 | [65 empty] | 90%
86 | [65 empty] | 90%
87 | [65 empty] | 90%
88 | [65 empty] | 90%
89 | [65 empty] | 90%
90 | [65 empty] | 90%
91 | [65 empty] | 90%
92 | [65 empty] | 90%
93 | [65 empty] | 90%
94 | [65 empty] | 90%
95 | [65 empty] | 90%
96 | [65 empty] | 90%
97 | [65 empty] | 90%
98 | [65 empty] | 90%
99 | [65 empty] | 90%
100 | [65 empty] | 90%
101 | [65 empty] | 90%
102 | [65 empty] | 90%
103 | [65 empty] | 90%
104 | [65 empty] | 90%
105 | [65 empty] | 90%
106 | [65 empty] | 90%
107 | [65 empty] | 90%
108 | [65 empty] | 90%
109 | [65 empty] | 90%
110 | [65 empty] | 90%
111 | [65 empty] | 90%
112 | [65 empty] | 90%
113 | [65 empty] | 90%
114 | [65 empty] | 90%
115 | [65 empty] | 90%
116 | [65 empty] | 90%
117 | [65 empty] | 90%
118 | [65 empty] | 90%
119 | [65 empty] | 90%
120 | [65 empty] | 90%
121 | [65 empty] | 90%
122 | [65 empty] | 90%
123 | [65 empty] | 90%
124 | [65 empty] | 90%
125 | [65 empty] | 90%
126 | [65 empty] | 90%
127 | [65 empty] | 90%
128 | [65 empty] | 90%
129 | [65 empty] | 90%
130 | [65 empty] | 90%
131 | [65 empty] | 90%
132 | [65 empty] | 90%
133 | [65 empty] | 90%
134 | [65 empty] | 90%
135 | [65 empty] | 90%
136 | [65 empty] | 90%
137 | [65 empty] | 90%
138 | [65 empty] | 90%
139 | [65 empty] | 90%
140 | [65 empty] | 90%
141 | [65 empty] | 90%
142 | [65 empty] | 90%
143 | [65 empty] | 90%
144 | [65 empty] | 90%
145 | [65 empty] | 90%
146 | [65 empty] | 90%
147 | [65 empty] | 90%
148 | [65 empty] | 90%
149 | [65 empty] | 90%
150 | [65 empty] | 90%
151 | [65 empty] | 90%
152 | [65 empty] | 90%
153 | [65 empty] | 90%
154 | [65 empty] | 90%
155 | [65 empty] | 90%
156 | [65 empty] | 90%
157 | [65 empty] | 90%
158 | [65 empty] | 90%
159 | [65 empty] | 90%
160 | [65 empty] | 90%
161 | [65 empty] | 90%
162 | [65 empty] | 90%
163 | [65 empty] | 90%
Formulas:
HSE TR Date = IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],"")))))))
CLIENT CM Date = IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],"")))))))))))))
Approved = IFERROR(IF([CLIENT CM Date]<>"","",TODAY()-[HSE TR Date]-14),"")
CLIENT = IF(OR([STATUS]="CODE 1"),"",IF(AND([VENDOR]<>"",[CLIENT CM Date]<>""),(TODAY()-[CLIENT CM Date]-7),IF([VENDOR]<>"","","")))

## filter package
|  | FILTER PACKAGE STYRENE PARK OFFSITE |  |  |  | Color Legend:
|  | Vendor Print Index & Schedule (VPIS) |  |  |  | Approved | CLIENT | VENDOR
PO No.:
VPIS Rev: 00 |  | MR No.: | PR No.: |  |  | LAST STATUS | [9 empty] | REV 00 | [6 empty] | REV 01 | [6 empty] | REV 02 | [6 empty] | REV 03 | [6 empty] | REV 04 | [6 empty] | REV 05 | [6 empty] | REV 06
Item No. | Document Number | Document Title | Type | Rev | Planned Issue Date | Client hand | HSE hand | Last Rev. | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | HSE TR No. | HSE TR Date | STATUS | CLIENT CM Date | HSE REP DATE | CLIENT RES TO REP DATE | REMARK | Weight Factor % |  | TO | TO | CC | CC | DONT TOUCH
1 | EI027-ENR-VD-GE-LST-001 | Vendor Print Index and Schedule (VPIS) for cartridge Filter |  | 1 |  |  |  | 1 | 5 | 2024-03-11 | APPROVED | 2024-03-13 |  |  |  | 1 | 2024-02-14 | [5 empty] | 5 | 2024-03-11 | APPROVED | 2024-03-13 | [39 empty] | 100% | [5 empty] | FALSE | FALSE
2 | EI027-ENR-VD-GE-LST-002 | Sub Vendor List for cartridge Filter |  | 0 |  |  |  | 0 | 34 | 2024-06-19 | [5 empty] | 34 | 2024-06-19 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
3 | EI027-ENR-VD-GE-SCH-003 | Project Time Schedule for cartridge Filter |  | 1 |  |  |  | 1 | 4 | 2024-03-11 | APPROVED | 2024-03-13 |  |  |  | 1 | 2024-02-21 | [5 empty] | 4 | 2024-03-11 | APPROVED | 2024-03-13 | [39 empty] | 90% | [5 empty] | FALSE | FALSE
4 | EI027-ENR-VD-GE-LST-004 | Commissioning Spare Part List for cartridge Filter | [63 empty] | 90% |  |  |  |  | STATUS LIST | FALSE | FALSE
5 | EI027-ENR-VD-GE-LST-005 | Two Years Operation Spare Parts List for cartridge Filter | [63 empty] | 90% |  |  |  |  | COMMENTED | FALSE | FALSE
6 | EI027-ENR-VD-GE-LST-006 | Final Book Index for cartridge Filter | [63 empty] | 90% |  |  |  |  | APPROVED | FALSE | FALSE
7 | EI027-ENR-VD-GE-LST-007 | Final Book for cartridge Filter | [63 empty] | 90% |  |  |  |  | NO COMMENT | FALSE | FALSE
8 | EI027-ENR-VD-QC-ITP-001 | Inspection And Test Plan for cartridge Filter |  | 2 |  |  |  | 2 | N | 2024-03-03 | APPROVED | 2024-03-03 |  |  |  | 1 | 2024-02-20 | [5 empty] | 1 | 2024-02-26 | [5 empty] | N | 2024-03-03 | APPROVED | 2024-03-03 | [32 empty] | 90% | [5 empty] | FALSE | FALSE
9 | EI027-ENR-VD-QC-PRO-002 | Welding Procedure Specification & Qualification Records for cartridge Filter |  | 0 |  |  |  | 0 | 6 | 2024-03-18 | [5 empty] | 6 | 2024-03-18 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
10 | EI027-ENR-VD-QC-PRO-003 | Preservation , Packaging, And Shipping Procedure for cartridge Filter |  | 0 |  |  |  | 0 | 18 | 2024-04-15 | [5 empty] | 18 | 2024-04-15 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
11 | EI027-ENR-VD-QC-PRO-004 | Test Procedures for cartridge Filter |  | 0 |  |  |  | 0 | 28 | 2024-06-11 | [5 empty] | 28 | 2024-06-11 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
12 | EI027-ENR-VD-PR-PRO-001 | Installation, Operating and Maintenance Manual for cartridge Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
13 | EI027-ENR-VD-PR-PFD-002 | PFD for cartridge Filter |  | 1 |  |  |  | 1 | 19 | 2024-04-16 | APPROVED | 2024-05-08 | 2024-05-20 |  |  | 1 | 2024-02-21 | COMMENTED | 2024-04-03 |  |  |  | 19 | 2024-04-16 | APPROVED | 2024-05-08 | 2024-05-20 | [38 empty] | 90% | [5 empty] | FALSE | FALSE
14 | EI027-ENR-VD-PR-PID-003 | P&ID for cartridge Filter |  | 3 |  |  |  | 3 | 22 | 2024-04-24 | APPROVED |  |  |  |  | 1 | 2024-02-21 | COMMENTED | 2024-03-03 | 2024-04-08 |  |  | 10 | 2024-04-08 | COMMENTED | 2024-04-14 |  |  |  | 15 | 2024-04-14 | COMMENTED | 2024-04-20 | 2024-04-24 |  |  | 22 | 2024-04-24 | APPROVED | [26 empty] | 90% | [5 empty] | FALSE | FALSE
15 | EI027-ENR-VD-PR-DCR-004 | Process Description for cartridge Filter |  | 1 |  |  |  | 1 | 21 | 2024-04-22 | APPROVED |  |  |  |  | 1 | 2024-02-21 | COMMENTED | 2024-03-03 | 2024-04-22 |  |  | 21 | 2024-04-22 | APPROVED | [40 empty] | 90% | [5 empty] | FALSE | FALSE
16 | EI027-ENR-VD-ME-DSH-001 | Equipment Data Sheet-cartridge Filter |  | 3 |  |  |  | 3 | 26 | 2024-05-20 | APPROVED |  |  |  |  | 1 | 2024-02-21 | COMMENTED | 2024-03-03 |  |  |  | 11 | 2024-04-08 | [5 empty] | 14 | 2024-04-14 | COMMENTED | 2024-04-20 | 2024-05-20 |  |  | 26 | 2024-05-20 | APPROVED | [26 empty] | 90% | [5 empty] | FALSE | FALSE
17 | EI027-ENR-VD-ME-CAL-003 | Strength Calculation-cartridge Filter |  | 1 |  |  |  | 1 | 8 | 2024-05-26 | APPROVED |  |  |  | 8-apr-24 Replaced | 1 | 2024-02-28 | COMMENTED | 2024-04-03 | 2024-04-08 |  |  | 8 | 2024-05-26 | APPROVED |  |  |  | 8-apr-24 Replaced | [36 empty] | 90% | [5 empty] | FALSE | FALSE
18 | EI027-ENR-VD-ME-DWG-005 | General Arrangement Drawing-cartridge Filter |  | 1 |  |  |  | 1 | 17 | 2024-05-26 | APPROVED |  |  |  | 15-apr-24 Replaced | 3 | 2024-03-06 | COMMENTED | 2024-03-16 | 2024-04-15 |  |  | 17 | 2024-05-26 | APPROVED |  |  |  | 15-apr-24 Replaced | [36 empty] | 90% | [5 empty] | FALSE | FALSE
19 | EI027-ENR-VD-ME-DWG-007 | Name Plate Drawing for cartridge Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
20 | EI027-ENR-VD-ME-DWG-008 | Ladder & Platform Drawing for cartridge Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
21 | EI027-ENR-VD-PI-DWG-001 | GAD For Package for cartridge Filter |  | 0 |  |  |  | 0 | 27 | 2024-05-26 | APPROVED |  |  |  |  | 27 | 2024-05-26 | APPROVED | [47 empty] | 90% | [5 empty] | FALSE | FALSE
22 | EI027-ENR-VD-PI-MTO-002 | MTO for Piping for cartridge Filter |  | 0 |  |  |  | 0 | 32 | 2024-06-19 | [5 empty] | 32 | 2024-06-19 | [48 empty] | 90% | [5 empty] | TRUE | FALSE
23 | EI027-ENR-VD-IN-LST-001 | Instrument List for cartridge Filter |  | 1 |  |  |  | 1 | 25 | 2024-04-30 | APPROVED |  |  |  | FI 19-jun-24 | 12 | 2024-04-13 | COMMENTED | 2024-04-23 | 2024-04-30 |  |  | 25 | 2024-04-30 | APPROVED |  |  |  | FI 19-jun-24 | [36 empty] | 90% | [5 empty] | FALSE | FALSE
24 | EI027-ENR-VD-IN-LST-002 | I\O List for cartridge Filter |  | 0 |  |  |  | 0 | 24 | 2024-04-29 | APPROVED |  |  |  | FI 19-jun-24 | 24 | 2024-04-29 | APPROVED |  |  |  | FI 19-jun-24 | [43 empty] | 90% | [5 empty] | FALSE | FALSE
25 | EI027-ENR-VD-IN-DSH-003 | Instrument Data Sheet for cartridge Filter |  | 0 |  |  |  | 0 | 20 | 2024-04-22 | APPROVED |  |  |  | FI 19-jun-24 | 20 | 2024-04-22 | APPROVED |  |  |  | FI 19-jun-24 | [43 empty] | 90% | [5 empty] | FALSE | FALSE
26 | EI027-ENR-VD-IN-DW G-004 | Hook Up Drawing for cartridge Filter |  | 0 |  |  |  | 0 | 23 | 2024-04-28 | APPROVED |  |  |  | FI 19-jun-24 | 23 | 2024-04-28 | APPROVED |  |  |  | FI 19-jun-24 | [43 empty] | 90% | [5 empty] | FALSE | FALSE
27 | EI027-ENR-VD-IN-LST-005 | Instrument Cable List for cartridge Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
28 | EI027-ENR-VD-IN-DW G-006 | Junction Boxes Wiring Diagrams And Outline Drawing for cartridge Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
29 | EI027-ENR-VD-CL-DW G-001 | Foundation Plans With Static/Dynamic Loads, And Bolts Detail for cartridge Filter | [63 empty] | 90% | [5 empty] | FALSE | FALSE
30 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
31 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
32 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
33 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
34 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
35 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
36 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
37 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
38 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
39 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
40 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
41 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
42 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
43 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
44 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
45 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
46 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
47 | [71 empty] | FALSE | FALSE
48 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
49 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
50 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
51 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
52 | [65 empty] | 90% | [5 empty] | FALSE | FALSE
52 | [65 empty] | 90%
53 | [65 empty] | 90%
54 | [65 empty] | 90%
55 | [65 empty] | 90%
56 | [65 empty] | 90%
57 | [65 empty] | 90%
58 | [65 empty] | 90%
59 | [65 empty] | 90%
60 | [65 empty] | 90%
61 | [65 empty] | 90%
62 | [65 empty] | 90%
63 | [65 empty] | 90%
64 | [65 empty] | 90%
65 | [65 empty] | 90%
66 | [65 empty] | 90%
67 | [65 empty] | 90%
68 | [65 empty] | 90%
69 | [65 empty] | 90%
70 | [65 empty] | 90%
71 | [65 empty] | 90%
72 | [65 empty] | 90%
73 | [65 empty] | 90%
74 | [65 empty] | 90%
75 | [65 empty] | 90%
76 | [65 empty] | 90%
77 | [65 empty] | 90%
78 | [65 empty] | 90%
79 | [65 empty] | 90%
80 | [65 empty] | 90%
81 | [65 empty] | 90%
82 | [65 empty] | 90%
83 | [65 empty] | 90%
84 | [65 empty] | 90%
85 | [65 empty] | 90%
86 | [65 empty] | 90%
87 | [65 empty] | 90%
88 | [65 empty] | 90%
89 | [65 empty] | 90%
90 | [65 empty] | 90%
91 | [65 empty] | 90%
92 | [65 empty] | 90%
93 | [65 empty] | 90%
94 | [65 empty] | 90%
95 | [65 empty] | 90%
96 | [65 empty] | 90%
97 | [65 empty] | 90%
98 | [65 empty] | 90%
99 | [65 empty] | 90%
100 | [65 empty] | 90%
101 | [65 empty] | 90%
102 | [65 empty] | 90%
103 | [65 empty] | 90%
104 | [65 empty] | 90%
105 | [65 empty] | 90%
106 | [65 empty] | 90%
107 | [65 empty] | 90%
108 | [65 empty] | 90%
109 | [65 empty] | 90%
110 | [65 empty] | 90%
111 | [65 empty] | 90%
112 | [65 empty] | 90%
113 | [65 empty] | 90%
114 | [65 empty] | 90%
115 | [65 empty] | 90%
116 | [65 empty] | 90%
117 | [65 empty] | 90%
118 | [65 empty] | 90%
119 | [65 empty] | 90%
120 | [65 empty] | 90%
121 | [65 empty] | 90%
122 | [65 empty] | 90%
123 | [65 empty] | 90%
124 | [65 empty] | 90%
125 | [65 empty] | 90%
126 | [65 empty] | 90%
127 | [65 empty] | 90%
128 | [65 empty] | 90%
129 | [65 empty] | 90%
130 | [65 empty] | 90%
131 | [65 empty] | 90%
132 | [65 empty] | 90%
133 | [65 empty] | 90%
134 | [65 empty] | 90%
135 | [65 empty] | 90%
136 | [65 empty] | 90%
137 | [65 empty] | 90%
138 | [65 empty] | 90%
139 | [65 empty] | 90%
140 | [65 empty] | 90%
141 | [65 empty] | 90%
142 | [65 empty] | 90%
143 | [65 empty] | 90%
144 | [65 empty] | 90%
145 | [65 empty] | 90%
146 | [65 empty] | 90%
147 | [65 empty] | 90%
148 | [65 empty] | 90%
149 | [65 empty] | 90%
150 | [65 empty] | 90%
151 | [65 empty] | 90%
152 | [65 empty] | 90%
153 | [65 empty] | 90%
154 | [65 empty] | 90%
155 | [65 empty] | 90%
156 | [65 empty] | 90%
157 | [65 empty] | 90%
158 | [65 empty] | 90%
159 | [65 empty] | 90%
160 | [65 empty] | 90%
161 | [65 empty] | 90%
162 | [65 empty] | 90%
163 | [65 empty] | 90%
Formulas:
HSE TR Date = IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],IF([HSE TR Date]<>"",[HSE TR Date],"")))))))
CLIENT CM Date = IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],IF([HSE TR Date]<>"","",IF([CLIENT CM Date]<>"",[CLIENT CM Date],"")))))))))))))
Approved = IFERROR(IF([CLIENT CM Date]<>"","",TODAY()-[HSE TR Date]-14),"")
CLIENT = IF(OR([STATUS]="CODE 1"),"",IF(AND([VENDOR]<>"",[CLIENT CM Date]<>""),(TODAY()-[CLIENT CM Date]-7),IF([VENDOR]<>"","","")))