## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Vendor Print Index & Schedule | N-278-VD-6019-GN-MDR-0001-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 01 | closed | LIDCO-PO-NEC-278-6019 | Noted
2 | 1 | 01 | closed | N278-000-ME-MR-1020-001 | Noted
3 | 1 | 01 | closed | High Pressure Air Compressor | Noted
4 | 1 | 01 | closed | Please add -pulsation study approach 1 calculation -rod load/gas load charts/curves -oil pump datasheet/drawing -oil heater datasheet/drawing -lifting procedure/drawing for shipping/installation | pulsation study approach 1 calculation, rod load/gas load charts/curves, oil pump datasheet/drawing, oil heater datasheet/drawing are all 4 included in document N-278-VD-6019-ME-DS-0010-01 Equipment Data Sheet lifting procedure/drawing for shipping/installation is included in document N-278-VD-6019-GN-PRC-0022-01 Preservation, Packing & Shipping Procedure
5 | 1 | 01 | closed | Vendor print index schedule | Noted
6 | 1 | 01 | closed | should be "IN" category | Noted, all category comments are changed
7 | 1 | 01 | closed | including material of all parts | That is included in this document N-278-VD-6019-ME-DS-0010-01 Equipment Data Sheet |  |  |  | Open
8 | 1 | 01 | closed | All motors | Yes, this is motor data sheet of all motors |  |  |  | Closed
9 | 1 | 01 | closed | to be Instrument Datasheet and Catalogue | Catalogue will not be provided as agreed in sales stage
10 | 1 | 01 | closed | General Note : Items in below should be added: - Outline Dimensional Drawings and wiring layout for for LCP Panel - Outline Dimensional Drawings and wiring diagram for Junction Box - Alarm and Set point List - Instruments Hook-Up Drawing - Control and shut down Logic Block Diagram - Instrument and Junction Box location layout drawings - Control Valve sizing sheet | Outline Dimensional Drawings and wiring layout for for LCP Panel Outline Dimensional Drawings and wiring diagram for Junction Box This is included in document N-278-VD-6019-IN-DIA-0004-01 and N-278-VD-6019-IN-DWG-0006-01 Alarm and Set point List included in document N-278-VD-6019-IN-LIS-0005-01 Instruments Hook-Up Drawing Noted will be included Control and shut down Logic Block Diagram Control and Shutdown is included in N-278-VD-6019-GN-PRO-0021-01 Instrument and Junction Box location layout drawings Included in N-278-VD-6019-PR-GAD-0003-01 Control Valve sizing sheet Not Applicable
11 | 1 | 01 | closed | Noise data sheet shall be added. | Noted
12 | 1 | 01 | closed | Should be renamed (refer to general note | Noted
13 | 1 | 01 | closed | To be specified for which equipment? | Applicable for all the parts agreed during sales stage
14 | 1 | 01 | closed | Control philosophy and Interlock Description | Noted
15 | 1 | 01 | closed | including calculation | Not agreed for coolers only for Pulsation dampers
16 | 1 | 01 | closed | Items in below should be added: -Line list -Bill of material (MTO) -Insulation MTO -Isometric drawing(if any) -3d model (compatible with STP or PML) | Line List will be included Insulation MTO is Not applicable Isometric drawing this is the same as 3D model 3D model will be included
17 | 1 | 01 | closed | below document should be added : 1- Inspection and test procedure for whole package Ins. 2- PMI procedure (if applicable) Ins. 3- Work Break Down Structure (WBS) Gen 4- Time Schedule Gen 5- Inspection Notification (Please consider this numbering (IN-278-6019) for this Doc. ) Ins. | 1, Is already there under S/R number 8 2, Not applicable 3, Not applicable 4, This is included in the monthly progress report 5, Noted, will be included