## Airpack VDS (hidden)
VENDOR DOCUMENT SCHEDULE
Project: |  |  | Integrated Methanol and Ammonia Plant |  |  |  |  | FA: For Approval |  | 1: Approved without comments
Purchase order: |  |  | LIDCO-PO-NEC-278-6019 |  |  |  |  | FI: For Information |  | 2: Approved with comments (VENDOR TO AMEND AND SUBMIT THE "FOR APPROVAL")
Airpack reference: |  |  | 17735-COM |  |  |  |  | AB: As Built |  | 3: COMMENTED. (VENDOR TO AMEND AND SUBMIT THE "FOR APPROVAL")
Project manager |  |  | Jochem Jongepier & Sander Klaassen |  |  |  |  | F: Final |  | 4: For information
Document turn around time: |  |  | 10 |  |  |  |  | CRS |  | 5: CRS
Airpack document number | Revision number | Contractor / Customer Document number | Description | Usage | Document issue date |  |  | Document return date |  | Aproval Code | Days of delay (5 days = 1 working week) | Transm. nr.
[5 empty] | Planned date | Scheduled date | Actual date | Planned date | Actual date
17735-01 | 01 | N-278-VD-6019-GN-MDR-0001-01 | Vendor Print Index and Schedule | FA | 2023-07-07 |  | 2023-07-07 | 2023-07-21 | 2023-07-17 | 2 | -5
17735-01 | 02 | N-278-VD-6019-GN-MDR-0001-01 | Vendor Print Index and Schedule | FA | 2023-07-31 | [5 empty] | #VALUE!
17735-03 | 01 | N-278-VD-6019-PR-PID-0002-01 | Piping & Instrument Diagram | FA | 2023-07-21 | [5 empty] | #VALUE!
17735-04 | 01 | N-278-VD-6019-PR-GAD-0003-01 | General Arrangement Drawing (incl foundation load details) | FA | 2023-09-29 | [5 empty] | #VALUE!
17735-05 | 01 | N-278-VD-6019-EL-DIA-0004-01 | Wiring Diagram (including Terminal Diagram) | FA | 2023-08-25 | [5 empty] | #VALUE!
17735-06 | 01 | N-278-VD-6019-EL-LIS-0005-01 | I/O List | FA | 2023-08-25 | [5 empty] | #VALUE!
17735-07 | 01 | N-278-VD-6019-EL-DWG-0006-01 | Panel Layout Drawing | FA | 2023-09-22 | [5 empty] | #VALUE!
17735-08 | 01 | N-278-VD-6019-GN-ITP-0007-01 | Inspection & Test Plan (ITP) | FA | 2023-07-21 | [5 empty] | #VALUE!
17735-09 | 01 | N-278-VD-6019-GN-UFD-0008-01 | Utility Consumption | FA | 2023-08-11 | [5 empty] | #VALUE!
17735-10 | 01 | N-278-VD-6019-PM-DS-0009-01 | Main Motor Data Sheets | FA | 2023-08-11 | [5 empty] | #VALUE!
17735-11A | 01 | N-278-VD-6019-ME-DS-0010-01 | Equipment Data Sheet | FA | 2023-09-01 | [5 empty] | #VALUE!
17735-11B | 01 | N-278-VD-6019-ME-DS-0011-01 | Inter / After Cooler Data Sheet | FA | 2023-09-01 | [5 empty] | -29
17735-12 | 01 | N-278-VD-6019-IN-DS-0012-01 | Instrument Data Sheets | FA | 2023-09-01 | [5 empty] | #VALUE!
17735-13 | 01 | N-278-VD-6019-GN-OTH-0013-01 | Commissioning and Start-up Spares | FI | 2023-07-28 | [5 empty] | #VALUE!
17735-14 | 01 | N-278-VD-6019-GN-PRC-0014-01 | FAT Procedure | FA | 2023-08-11 | [5 empty] | #VALUE!
17735-15 | 01 | N-278-VD-6019-GN-PRC-0015-01 | NDE Procedure | FA | 2023-08-11 | [5 empty] | #VALUE!
17735-16 | 01 | N-278-VD-6019-GN-DWG-0016-01 | Package Nameplate Drawing | FA | 2023-10-11 | [5 empty] | #VALUE!
17735-17 | 01 | N-278-VD-6019-GN-PRC-0017-01 | Hydrotest procedure | FA | 2023-08-25 | [5 empty] | #VALUE!
17735-18 | 01 | N-278-VD-6019-GN-PRC-0018-01 | Painting Procedure | FA | 2023-08-25 | [5 empty] | #VALUE!
17735-19 | 01 | N-278-VD-6019-GN-LIS-0019-01 | Index of Data Book | FA | 2023-09-04 | [5 empty] | #VALUE!
17735-20 | 01 | N-278-VD-6019-GN-LIS-0020-01 | Index of Instruction and Operating Manual | FA | 2023-09-20 | [5 empty] | #VALUE!
17735-21 | 01 | N-278-VD-6019-GN-PRO-0021-01 | Control Philosophy | FA | 2023-08-25 | [5 empty] | #VALUE!
17735-22 | 01 | N-278-VD-6019-GN-PRC-0022-01 | Preservation, Packing & Shipping Procedure | FA | 2023-08-22 | [5 empty] | #VALUE!
17735-23A | 01 | N-278-VD-6019-ME-DWG-0023-01 | Detail Drawings for Coolers | FA | 2023-09-15 | [5 empty] | #VALUE!
17735-23B | 01 | N-278-VD-6019-ME-DWG-0024-01 | Detail Drawings for Pulsation Dampers | FA | 2023-09-15 | [5 empty] | #VALUE!
17735-24 | 01 | N-278-VD-6019-ME-CAL-0025-01 | Pulsation Damper Design Calculations | FI | 2023-09-15 | [5 empty] | #VALUE!
17735-25 | 01 | N-278-VD-6019-GN-WS-0026-01 | PQR / WPS | FI | 2023-08-25 | [5 empty] | #VALUE!
17735-26 | 01 | N-278-VD-6019-GN-WS-0027-01 | WPQ | FI | 2023-08-25 | [5 empty] | #VALUE!
17735-27 | 01 | N-278-VD-6019-GN-SF-0028-01 | Cause & Effect Chart | FA | 2023-09-08 | [5 empty] | #VALUE!
17735-28 | 01 | N-278-VD-6019-GN-OTH-0029-01 | Tie-in Nozzle Loads | FI | 2023-10-10 | [5 empty] | #VALUE!
17735-30 | 01 | N-278-VD-6019-EL-DIA-0030-01 | Loop diagrams | FA | 2023-09-22 | [5 empty] | #VALUE!
17735-33 | 01 | N-278-VD-6019-GN-PRC-0031-01 | (Pre-) Commissioning Procedure | FA | 2023-09-15 | [5 empty] | #VALUE!
17735-35 | 01 | N-278-VD-6019-IN-LIS-0032-01 | Instrument List | FA | 2023-09-15 | [5 empty] | #VALUE!
17735-37 | 01 | N-278-VD-6019-GN-MNL-0033-01 | Quality Manual | FI | 2023-08-04 | [5 empty] | #VALUE!
17735-41 | 01 | N-278-VD-6019-EL-DIA-0034-01 | Earthing Diagrams | FA | 2023-09-22 | [5 empty] | #VALUE!
17735-42 | 01 | N-278-VD-6019-GN-OTH-0035-01 | Spare Parts for 2 years Operation (SPIR) | FI | 2023-12-29 | [5 empty] | #VALUE!
17735-43 | 01 | N-278-VD-6019-GN-EQL-0036-01 | Sub-Supplier List | FA | 2023-08-04 | [5 empty] | #VALUE!
17735-46 | 01 | N-278-VD-6019-IN-DS-0037-01 | PSV Data Sheets | FA | 2023-09-22 | [5 empty] | -44
17735-47 | 01 | N-278-VD-6019-IN-CAL-0038-01 | PSV sizing calculations | FA | 2023-12-15 | [5 empty] | -104
17735-48 | 01 | N-278-VD-6019-IN-DS-0039-01 | Valve Data Sheets | FA | 2023-09-22 | [5 empty] | -44
17735-51 | 01 | N-278-VD-6019-PR-LIS-0040-01 | Lubrication List | FA | 2023-09-29 | [5 empty] | -49
17735-52 | 01 | N-278-VD-6019-EL-SCH-0041-01 | Cable schedule | FA | 2023-09-29 | [5 empty] | -49
17735-58 | 01 | N-278-VD-6019-GN-MNL-0045-01 | Manufacturing Record Book MRB | FI | AFTER FAT | [5 empty] | #VALUE!
17735-59 | 01 | N-278-VD-6019-GN-MNL-0046-01 | Technical Operating and Maintenance Manual | FI | AFTER FAT | [5 empty] | #VALUE!
Formulas:
FA: For Approval = IF(ISBLANK([Actual date]),"",WORKDAY([Actual date],D6))
Days of delay (5 days = 1 working week) = IF([Usage]=0,"",IF(AND([Actual date]=0,[FA: For Approval]=0,[Actual date]=0),NETWORKDAYS([Document issue date],TODAY()),IF(AND([FA: For Approval]>0,[Actual date]>0),NETWORKDAYS([FA: For Approval],[Actual date]),IF([FA: For Approval]>0,NETWORKDAYS([FA: For Approval],TODAY()),""))))
Document issue date = WORKDAY([Actual date, row above],D6)

## 100
LIDCO INTERGRATED AMMONIA & METHANOl |  | VENDOR PRINT INDEX & SCHEDULE
VENDOR Name
LEGEND OF REVIEW CODE
P/O NO. : |  | LIDCO-PO-NEC-278-6019 | ISSUE DATE : |  | 2023-07-25 | [6 empty] | CODE 1 : APPROVED.
EQUIPMENT NAME |  | High Pressure Air Compressor | [9 empty] | CODE 2 : APPROVED WITH COMMENTS. (VENDOR TO AMEND AND SUBMIT THE "FOR APPROVAL")
|  |  | MR NO. : |  | N278-000-ME-MR-1020-001 | [6 empty] | CODE 3 : COMMENTED. (VENDOR TO AMEND AND SUBMIT THE "FOR APPROVAL")
S/R NO | .Purchaser Doc No. | DOCUMENT TITLE | VP Category | Forecast Date |  | REV. 0 |  |  | REV. 1 |  |  | REV. 2 |  |  | REV. 3 |  |  | REV. 4 |  |  | REV. 5
| Vendor Doc No |  |  |  |  | VENDOR | PURCHASER | REVIEW CODE | VENDOR | PURCHASER | REVIEW CODE | VENDOR | PURCHASER | REVIEW CODE | VENDOR | PURCHASER | REVIEW CODE | VENDOR | PURCHASER | REVIEW CODE | VENDOR | PURCHASER | REVIEW CODE
1 | N-278-VD-6019-GN-MDR-0001-01 | Vendor Print Index & Schedule | Eng/Ins | 2023-07-07
17735-01
2 | N-278-VD-6019-PR-PID-0002-01 | Piping & Instrument Diagram | Eng | 2023-07-21
17735-03
3 | N-278-VD-6019-PR-GAD-0003-01 | General Arrangement Drawing (incl foundation load details) | Eng | 2023-09-29
17735-04
4 | N-278-VD-6019-PR-GAD-0004-01 | 3D model (STP) | Eng | 2023-09-29
17735-04A
5 | N-278-VD-6019-IN-DIA-0005-01 | Wiring Diagram (including Terminal Diagram) for LCP Panel and Junction Box | Eng | 2023-08-25
17735-05
6 | N-278-VD-6019-IN-LIS-0006-01 | I/O List | Eng | 2023-08-25
17735-06
7 | N-278-VD-6019-IN-DWG-0007-01 | Outline Dimensional Drawings for LCP Panel and Junction Box | Eng | 2023-09-22
17735-07
8 | N-278-VD-6019-GN-ITP-0008-01 | Inspection & Test Plan (ITP) | Eng/Ins | 2023-07-21
17735-08
9 | N-278-VD-6019-GN-UFD-0009-01 | Utility Consumption | Eng | 2023-08-11
17735-09
10 | N-278-VD-6019-PM-DS-0010-01 | Main Motor Data Sheet | Eng | 2023-08-11
17735-10
11 | N-278-VD-6019-ME-DS-0011-01 | Equipment Data Sheet | Eng | 2023-09-01
17735-11A
12 | N-278-VD-6019-ME-DS-0012-01 | Inter / After Cooler Data Sheet | Eng | 2023-09-01
17735-11B
13 | N-278-VD-6019-IN-DS-0013-01 | Instrument Data Sheet | Eng | 2023-09-01
17735-12
14 | N-278-VD-6019-GN-OTH-0014-01 | Commissioning and Start-up Spares | Eng | 2023-07-28
17735-13
15 | N-278-VD-6019-GN-PRC-0015-01 | FAT Procedure | Eng/Ins | 2023-08-11
17735-14
16 | N-278-VD-6019-GN-PRC-0016-01 | NDE Procedure | INS | 2023-08-11
17735-15
17 | N-278-VD-6019-GN-DWG-0017-01 | Package Nameplate Drawing | Eng | 2023-10-11
17735-16
18 | N-278-VD-6019-GN-PRC-0018-01 | Hydrotest Procedure | INS | 2023-08-25
17735-17
19 | N-278-VD-6019-GN-PRC-0019-01 | Surface Preparation and Painting Procedure | Eng | 2023-08-25
17735-18
20 | N-278-VD-6019-GN-LIS-0020-01 | Index of Vendor Data Book | Eng/Ins | 2023-09-04
17735-19
21 | N-278-VD-6019-GN-LIS-0021-01 | Index of Instruction and Operating Manual | Eng | 2023-09-20
17735-20
22 | N-278-VD-6019-GN-PRO-0022-01 | Control philosophy and Interlock Description | Eng | 2023-08-25
17735-21
23 | N-278-VD-6019-GN-PRC-0023-01 | Preservation, Packing & Shipping Procedure | Eng | 2023-08-22
17735-22
24 | N-278-VD-6019-ME-DWG-0024-01 | Detail Drawings for Coolers | Eng | 2023-09-15
17735-23A
25 | N-278-VD-6019-ME-DWG-0025-01 | Detail Drawings for Pulsation Dampers | Eng | 2023-09-15
17735-23B
26 | N-278-VD-6019-ME-CAL-0026-01 | Pulsation Damper Design Calculations | Eng | 2023-09-15
17735-24
27 | N-278-VD-6019-GN-WS-0027-01 | Welding Book (PQR / WPS) | Eng/Ins | 2023-08-25
17735-25
28 | N-278-VD-6019-GN-WS-0028-01 | WPQ | INS | 2023-08-25
17735-26
29 | N-278-VD-6019-GN-SF-0029-01 | Cause & Effect Chart | Eng | 2023-09-08
17735-27
30 | N-278-VD-6019-GN-OTH-0030-01 | Tie-in Nozzle Loads | Eng | 2023-10-10
17735-28
31 | N-278-VD-6019-EL-DIA-0031-01 | Loop Diagrams | Eng | 2023-09-22
17735-30
32 | N-278-VD-6019-GN-PRC-0032-01 | (Pre-) Commissioning Procedure | Eng | 2023-09-15
17735-33
33 | N-278-VD-6019-IN-LIS-0033-01 | Instrument Index | Eng | 2023-09-15
17735-35
34 | N-278-VD-6019-GN-MNL-0034-01 | Quality Manual | INS | 2023-08-04
17735-37
35 | N-278-VD-6019-IN-DWG-0035-01 | Instrument Hook-up Drawing | INS | 2023-08-04
17735-38
36 | N-278-VD-6019-EL-DIA-0036-01 | Earthing Diagrams | Eng | 2023-09-22
17735-41
37 | N-278-VD-6019-GN-OTH-0037-01 | Spare Parts for 2 years Operation (SPIR) | Eng | 2023-12-29
17735-42
38 | N-278-VD-6019-GN-EQL-0038-01 | Sub-Supplier List | Eng/Ins | 2023-08-04
17735-43
39 | N-278-VD-6019-IN-DS-0039-01 | PSV Data Sheets | Eng | 2023-09-22
17735-46
40 | N-278-VD-6019-IN-CAL-0040-01 | PSV sizing calculations | Eng | 2023-12-15
17735-47
41 | N-278-VD-6019-IN-DS-0041-01 | Control Valve Data Sheet | Eng | 2023-09-22
17735-48
42 | N-278-VD-6019-IN-DS-0042-01 | Noise Data Sheet | Eng | After FAT
17735-49
43 | N-278-VD-6019-PR-LIS-0043-01 | Lubrication List | Eng | 2023-09-29
17735-51
44 | N-278-VD-6019-IN-SCH-0044-01 | Instrument Cable Schedule | Eng | 2023-09-29
17735-52
45 | N-278-VD-6019-GN-MNL-0045-01 | Vendor Data book | INS | After FAT
17735-58
46 | N-278-VD-6019-GN-MNL-0046-01 | Technical Operating and Maintenance Manual | Eng | After FAT
17735-59
47 | N-278-VD-6019-GN-MRP-0047-01 | Monthly Progress Report | Eng | Monthly
17735-60
48 | N-278-VD-6019-IN-LIS-0048-01 | Line List | INS | 2023-09-29
17735-61
48 | IN-278-6019 | Inspection Notification | Eng
17735-62