## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Vendor Print Index & Schedule | N-278-VD-6019-GN-MDR-0001-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 01 | closed | LIDCO-PO-NEC-278-6019 | Noted
2 | 1 | 01 | closed | N278-000-ME-MR-1020-001 | Noted
3 | 1 | 01 | closed | High Pressure Air Compressor | Noted
4 | 1 | 01 | closed | Please add -pulsation study approach 1 calculation -rod load/gas load charts/curves -oil pump datasheet/drawing -oil heater datasheet/drawing -lifting procedure/drawing for shipping/installation | pulsation study approach 1 calculation, rod load/gas load charts/curves, oil pump datasheet/drawing, oil heater datasheet/drawing are all 4 included in document N-278-VD-6019-ME-DS-0010-01 Equipment Data Sheet lifting procedure/drawing for shipping/installation is included in document N-278-VD-6019-GN-PRC-0022-01 Preservation, Packing & Shipping Procedure | Noted. So please change the document to "equipment datasheet (including, material of all parts, pulsation study, rod/gas loads/charts/curves, oil pump datasheet/drawing, oil heater datasheet/drawing)" -Since preservation/packing is related to another department, you are kindly requested to consider a separate doc for "lifting/shipping/installation/preservation procedure and drawing " | The document N-278-VD-6019-ME-DS-0010-01 Equipment Data Sheet had all the needed data of the equipment, including about the compressor. rod load/gas load charts/curves: Not available for this small compressor. oil pump and oil heater datasheet/drawing: This is part of the compressor and is therefor not included. As requested, for the pulsation study there is made a seperate document N-278-VD-6019-ME-CAL-0026-01 17735-24 The doucment N-278-VD-6019-GN-PRC-0022-01 Preservation, Packing & Shipping Procedure will be enough to prevent double documements. For installation the databook and manual has all the needed information to install the package. | Rod load/gas load charts/curves: Noted. Will be discussed in datasheet reviwed. Oil pump, oil heater: Please refer to the agreements at bid stage. Vendor confirmed to be provided. Lfting procedure: Vendor stated that lifting procedure is included in manual. Please note as per agreed SDRS, lifting procedure is a separate document. please consider a separate doc.
5 | 1 | 01 | closed | Vendor print index schedule | Noted
6 | 1 | 01 | closed | should be "IN" category | Noted, all category comments are changed
7 | 1 | 01 | closed | including material of all parts | That is included in this document N-278-VD-6019-ME-DS-0010-01 Equipment Data Sheet | and we referred to same doc. |  |  | Open
8 | 1 | 01 | closed | All motors | Yes, this is motor data sheet of all motors | It is mention main motordatasheet. If there is any other motor (e.g. motor of fan for cooling) it shall be included as well. | There is one motor in the package, which is LV main motor. The auxiliary motor is very small (120W) and located in the compressor to cool the cylinders. this motor is part of the compressor and therefor no data available. Name of datasheet is correct since this is only for the main motor. |  | Closed
9 | 1 | 01 | closed | to be Instrument Datasheet and Catalogue | Catalogue will not be provided as agreed in sales stage | for datasheet final Approved, cataloge should be attached to the document.
10 | 1 | 01 | closed | General Note : Items in below should be added: - Outline Dimensional Drawings and wiring layout for for LCP Panel - Outline Dimensional Drawings and wiring diagram for Junction Box - Alarm and Set point List - Instruments Hook-Up Drawing - Control and shut down Logic Block Diagram - Instrument and Junction Box location layout drawings - Control Valve sizing sheet | Outline Dimensional Drawings and wiring layout for for LCP Panel Outline Dimensional Drawings and wiring diagram for Junction Box This is included in document N-278-VD-6019-IN-DIA-0004-01 and N-278-VD-6019-IN-DWG-0006-01 Alarm and Set point List included in document N-278-VD-6019-IN-LIS-0005-01 Instruments Hook-Up Drawing Noted will be included Control and shut down Logic Block Diagram Control and Shutdown is included in N-278-VD-6019-GN-PRO-0021-01 Instrument and Junction Box location layout drawings Included in N-278-VD-6019-PR-GAD-0003-01 Control Valve sizing sheet Not Applicable | - Confirmed - Confirmed - Confirmed - Not acceptable .A separate Document for Control and shutdown logic block diagram shall be considered in VPIS. - Confirmed. - As per PID , PCV is including in package scope, so relevant sizing sheet shall be submitted too (could be included in relevant data sheet) Referred doc for Alarm and trip set point list (N-278-VD-6019-IN-LIS-0005-01) is not exist in VPIS,
11 | 1 | 01 | closed | Noise data sheet shall be added. | Noted
12 | 1 | 01 | closed | Should be renamed (refer to general note | Noted
13 | 1 | 01 | closed | To be specified for which equipment? | Applicable for all the parts agreed during sales stage
14 | 1 | 01 | closed | Control philosophy and Interlock Description | Noted
15 | 1 | 01 | closed | including calculation | Not agreed for coolers only for Pulsation dampers
16 | 1 | 01 | closed | Items in below should be added: -Line list -Bill of material (MTO) -Insulation MTO -Isometric drawing(if any) -3d model (compatible with STP or PML) | Line List will be included Insulation MTO is Not applicable Isometric drawing this is the same as 3D model 3D model will be included
17 | 1 | 01 | closed | below document should be added : 1- Inspection and test procedure for whole package Ins. 2- PMI procedure (if applicable) Ins. 3- Work Break Down Structure (WBS) Gen 4- Time Schedule Gen 5- Inspection Notification (Please consider this numbering (IN-278-6019) for this Doc. ) Ins. | 1, Is already there under S/R number 8 2, Not applicable 3, Not applicable 4, This is included in the monthly progress report 5, Noted, will be included | 1-Inspection and test procedure is different from inspection and test plan. Vendor shall submit it. 2-PMI test noted. 3- to be prepared 4- Trime schedule is different from Montly Progress Report. This doc. is a plan for whole package, updted time schedule shpld be submitted along with MPR. 5-Noted
18 | 1 | 02 | Open | Time schedule to be added | After PIM a production slot will be booked and the planning is shared. Any update on the planning be shared. For this purpose we have the monthly progress report.
19 | 1 | 02 | Open | HAZOP close out report shall be added | HAZOP is not in our scope, close out report to be provided by contractor |  |  | vendor shall participate in hazop study meeting and responsible for all hazop study outcomes and shall submit filled hazop action sheet accordingly.
20 | 1 | 02 | Open | It is mention main motor datasheet. If there is any other motor (eg. motor of fan for cooling) it shall be included as well. | There is one motor in the package, which is LV main motor. The auxiliary motor is very small (120W) and located in the compressor to cool the cylinders. this motor is part of the compressor and therefor no data available. Name of datasheet is correct since this is only for the main motor.
21 | 1 | 02 | Open | equipment datasheet (including, material of all parts, pulsation study, rod/gas loads/charts/curves, oil pump datasheet/drawing, oil heater datasheet/drawing) | "The document N-278-VD-6019-ME-DS-0010-01 Equipment Data Sheet had all the needed data of the equipment, including about the compressor. rod load/gas load charts/curves: Not available for this small compressor. oil pump and oil heater datasheet/drawing: This is part of the compressor and is therefor not included. As requested, for the pulsation study there is made a seperate document N-278-VD-6019-ME-CAL-0026-01 17735-24
22 | 1 | 02 | Closed | Please also mention in parantheses (full unit mechanical run test procedure) | Noted, incorporated
23 | 1 | 02 | Open | As stated in reply sheet please kindly consider two docs: -packing and marking procedure (INS) -lifting/shipping/installation/preservation procedure and drawing (Eng). | The doucment N-278-VD-6019-GN-PRC-0022-01 Preservation, Packing & Shipping Procedure will be enough to prevent double documements. For installation the databook and manual has all the needed information to install the package.
24 | 1 | 02 | Open | and welding/NDE map | It is a small skid with a few NDE documents, so not needed. only NDE procedures will be provided | Noted.
25 | 1 | 02 | Open | In last revision we commented to remove the 'weldmap for skid and piping'/ Please ignore our previous comment and please add it. | Weldmap is not available
26 | 1 | 02 | Closed | Control and shut down Logic Block Diagram shall be added to VPIS | Control and shut down Logic Block Diagram added
27 | 1 | 02 | Closed | Eng | Noted, incorporated
28 | 1 | 02 | Closed | Ins | Noted, incorporated