## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | P&ID | N-278-VD-6019-PR-PID-0002-01
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 02 | Closed | The tittle of the document (including package tag Number) on the first page to be provided | Incorporated | Closed
2 | 1 | 02 | Closed | Symbol and legend shall be added, or project symbol and legend shall be followed | legend and symbol are added (page 3 and 4) symbols are youre standard. | Closed
3 | 1 | 02 | Closed | Numbering of piping, instruments and equipment Tag Nrs shall be based on project specification | Incorporated | Closed
4 | 3 | 02 | Closed | It conflicts with our tag numbers, to be corrected. | Incorporated | Closed
5 | 3 | 02 | Closed | OT: 46° C DT:75 °C | Incorporated | Closed
6 | 3 | 02 | Closed | The inlet and outlet size of all PSVs to be specified. | They are specified in the document 17735-46 PSV datasheet (the outlet will be vendor to approve) For youre information the inlet is as per piping size 3/4" flanged outlet is atmosferic will be be calculated. | Closed
7 | 3 | 02 | Closed | LO isolation Valve shall be considered for all PSVs. | This is not aggreed in the contract. It is also not reccomended. It is not needed for this package. | Noted. |  |  | Open
8 | 3 | 02 | Closed | Compressor shall not be started at the Low Low suction pressure. I.e. Permissive to start signal shall be generated from NOT low low condition of suction pressure. | PALL means low trip when the suction pressure is below 6,5 bar the compressor will tripp and the package will stop immediately without cooling down. Compressor can be started with the start sequence described in control philosophy. | Trip command shall be shown via relevant interlock no. (IP-920). Refer to below sample shematic | Trip command is added with interlock no. IP-920 in the next revision
9 | 3 | 02 | Closed | Size of all Lines shall be added in PID. | Incorporated It is reccomended to add not to much information to keep a good over vieuw on the P&ID (especially the main lines are 1' or 3/4' | Closed
10 | 3 | 02 | Closed | Set = 7 barg | Incorporated | Closed
11 | 3 | 02 | Closed | Set point for PCV shall be specified | Incorporated | Closed
12 | 3 | 02 | Closed | Positioner for control valve with related alarm in control room will be considered. | Incorporated | Not implemented in PID. Positioner shall be shown such as below: | Positioner is updated. The instrument air to control the valve is taken from the inlet.
13 | 3 | 02 | Closed | Outlet T shall be specified | Incorporated it is specified at 60ºC | Closed
14 | 3 | 02 | Closed | TG and Globe valve shall be considered | A TG and Globe valve are not necessary because of TG 8205. | Separate TG for each exchanger shall be considered. Please relocate TG-8205 for one of the exchangers and add another TG for the 2nd one | Updated
15 | 3 | 02 | Closed | Cooling rate shall be specified | 1m3/h | Closed
16 | 3 | 02 | Closed | P&ID for High Pressure Air Compressor K020 | Incorporated | Closed
17 | 3 | 02 | Closed | DP of tube side also shall be specified. 10/13 rule shall be considered or PSV shall be installed | Incorporated | Closed
18 | 3 | 02 | Closed | Set = 75 °C | Incorporated | Closed
19 | 3 | 02 | Closed | All design temperature shall be checked based on project sizing criteria: - Maximum operating temperature +15 °C - Design temperature shall be rounded up to full 5 °C steps. | Incorporated | Refer to comment on PID | Inlet Desgin pressure is 75°C as per comment on rev.01 Other is updated as per comment
20 | 3 | 02 | Closed | Interlock IP922 / IP920 from process for package start / stop shall be shown. | Interlock not required for start stops | Vendor reply is not acceptable. Relevant signals shall be considered for compressor start / stop | Three interlocks are added. START, STOP and ESD.
21 | 3 | 02 | Closed | please recheck the ratio of design pressure to operating pressure to ascertain that PSV does not act during normal operation (because of pressure pulsation in the discharge side of compressor. In other words, Design pressure of inter stage equipment, Instruments and piping shall be rechecked. Distance between design and normal pressure is lower than 10 %”. | Incorporated | For second stage suction pulsation damper, please refer to comment on Pdf file. | Noted
22 | 3 | 02 | Closed | comment for both coolers: Vent/drain with valve to be considered on both sides. MOM: vent/drain for water side and drain for gas side will be added | A drain and vent on the coolers is not possible by the cooler suplier. There is a vent before and after in the water system. | Please also add drain on Air side (if on cooler not possible, on line) (the shell side can be drained in case of any tube rapture after years.) Please also confirm that water side of cooler can be drained/vented with those considered on water lines | Drain on the air side of the cooler is not needed since the gas is instrument air there will be no water in the air piping. Also the pulsation dampenters in line with the cooler have drains. Since the water system on the compressor is very small there is a drain added at the lowest point of the water system. from there the water system can be drained. For maintenance the complete air piping can be closed with valves and the water piping can be closed with valves. Both process lines can be drained In conclusion the air and water piping can be closed and drained to perform maintenance on the compressor. Because it is a very small compressor and almost no piping length this is sufficient for the design.
23 | 3 | 02 | Closed | All tags, Should be mentioned as per sample | Incorporated
24 | 3 | 02 | Closed | Skids should be Considered or move here | Not drawn as per Airpack standard
25 | 3 | 02 | Closed | All suffix tag should be start 82XX | Incorporated it is added in the notes
26 | 3 | 02 | Closed | All abbreviations should be mentioned in legend page | Incorporated
27 | 4 | 02 | Closed | As per VPIS should be renamed to LCP | Incorporated |  | Since there is no PLC inside the panel, and therefor no control of the package. It is named LPS, Local Pushbutton Station.
28 | 4 | 02 | Closed | All instruments tag should follow project spec (N278-000-CI-JSD-1500-001-02) | Updated according to e-mails
29 | 4 | 02 | Closed | Is it shaft driven?(if motor drive, to be added in consumption list) | It is shaft driven motor | Please add a note to avoid mis-understanding. | Updated in the next revision
REV. 03
30 | 1 | 03 | Closed | - All previous comment should be implemented and If any comments is not applicable please send reply sheet. - all Tag name in all documents should be same format. no needs "-" after prefix 320. example correct format is 320TT-8201 | - Noted - Please recheck where this is specified. It is a big change to update all the documents tags, and late to comment this in revision 3
31 | 2 | 03 | Closed | Modify to sight glass | Incorporated
32 | 2 | 03 | Closed | Battery Limit | All signals, dashed lines is Client scope. Note 9 is added to the P&ID
33 | 2 | 03 | Closed | symbol selector switch should be added | Incorporated
34 | 3 | 03 | Closed | Line number shall be added in PID According to legend of project.(Attachment#2) | Incorporated
35 | 3 | 03 | Closed | All PSV and CV Sizes will be finalized after the approval Instrument calculation sheet document. | Noted.
36 | 3 | 03 | Closed | All monitoring signals, shall be shown with battery limit. | All signals, dashed lines is Client scope. Note 9 is added to the P&ID
37 | 3 | 03 | Closed | Operating and Design condition for shell and tube side to be specified. | This will be specified in the datasheet
38 | 3 | 03 | Closed | should be followed according to legend (Attachment#1) Should be implemented for all PSV | Incorporated
39 | 3 | 03 | Closed | Please clarify. It seems this valve is considered for start the compressor. So, you are requested to recheck the set pressure. In addition please refer to process comment. | It is not a load / unload valve. The PCV is to keep the outlet pressure at 30 bar, as required. The valve opens and closes by a certain percentage the bypass to control the outlet pressure at 30 bar. When starting the package the valve is automatically closed, till the outlet reaches 30 bar. This sequence is also described in the controll philosophy and will be in the logic
40 | 3 | 03 | Closed | Process: Vendor is requested to clarify PCV requiement. Anyhow, it seems the PCV set pressure to be define a bit more that normal discharge pressrue to prevent valve opening at normal condition | Please refer to the control philosophy and logic for the controlling of the package
41 | 3 | 03 | Closed | Re-Comment: Ground!!? Clarify | Updated in the next revision to make it more clear. There is piping connected to direct the water flow down in case of an emergency.
42 | 3 | 03 | Closed | Please clarify about this. As per TCL B7, Suction pulsation suppression devices shall be designed for the same design pressure as the discharge pulsation suppression devices except when protected by a relief valve | Updated in the next revision to the design pressure of the pulsation dampener 1st stage discharge
43 | 3 | 03 | Closed | All monitoring signals, shall be shown with battery limit. | All signals, dashed lines is Client scope. Note 9 is added to the P&ID
44 | 3 | 03 | Closed | PCV or PV ? should be clarify . PCV do not receive electrical signals | PCV (pressure control valve) is an electric pneumatic controlled valve so you also need an electric signal. Please find this information in the datasheet
45 | 3 | 03 | Closed | As per project specification, thermowells shall be installed at least on 6" line size. | It is not possible to go from 3/4'' to 6'' because of the flow. We discussed this internal and decided we can design it to 4'' as absolute maximum. So thermowells are installed at 4'' piping in the next revision. And most thermowells, where possible are mounted on vessels, since they are bigger than 6".
46 | 3 | 03 | Closed | plz clarify and determine status and command signals related to Electric motor/Fan motor/Oil Pump | This is described in the Control philosophy Airpack ref. 17735-21.
47 | 3 | 03 | Closed | plz mention tag for SG | Tag no is provided for piping sight glasses. Sight glass in the oil sump is not replacable, but build in the equipment, so therefor not given any tag
48 | 4 | 03 | Closed | Tag name should be modified. 300LP-820 300JDAN-820 | Not incorporated. This is a new tag no, submitted in revision 3. and it is the 2nd time we are changing tags. All the tags are already defined in documents, therefor it is not possible to change. On this package is a JB (junctionbox) and a LPS (Local pushbutton station) It is this name to mention that there is no power or control from the box/station but provided from the DCS.
49 | 4 | 03 | Closed | These signals shall be sent from LPS to DCS. Please separate from other | This is not correct the signals must be in line with eachother and will have the same tag as the lights it is connected to. The signal is 24V to power the light XL-xxxx, coming from the DCS, so arrow up. The ESD must be there, it is required on the package. When a trip occurs the package will do an emergency stop. so this is the same sequence.
50 | 4 | 03 | Closed | As per PID of project, interlocks and tag name (ML/XA/YL) should be modified | Not applicable see comment 49
51 | 4 | 03 | Closed | Prefix "320" to be added to all instruments tag Number. | Note is changed to only instruments prefix
52 | 4 | 03 | Closed | Globe valve shall be considered | If there will be a globe valve it will have no function/use. If you design a globe valve in that place you can stop the waterflow in the aftercooler, if the valve fails and reduce the flow it will cause more tripps if the package is running.
53 | 3 | 03 | Closed | PZLC 8201 | Incorporated
54
55