## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | IO list | N-278-VD-6019-IN-LIS-0006-01 (17735-06)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 3 | 01 |  | please clarify compressor sysrem type | Location of instrument. (collum can be deleted?) | Noted
2 | Page 3 | 01 |  | all interface signals and commands between mcc and local panel to be added | Incorporated | Noted
3 | Page 3 | 01 |  | Should be revised according to comments of PID (Rename Tag) | Incorporated | Noted
4 | Page 3 | 01 |  | This data should be included in data sheet document not in index (Process connection, TW and isolation valve column). Please remove it from this document | Incorporated | Noted
5 | Page 3 | 01 |  | NC/NO, redundancy ,IS/NIS, DCS/ESD column should be added the table. | Added to table | Noted
6 | Page 3 | 01 |  | 24 VDC | Incorporated | Noted
7 | Page 3 | 01 |  | Field | Incorporated | Noted |  |  | Open
Closed