## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | ITP CRS | 17735-08
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2 | AirPack's Reply #3 | Client Reply #3
1 | Page 1 | 01 | Closed | Inspection and Test Plan for Air Compressor Package (K-020) | Title is added in the next revision | Noted.
2 | Page 3 | 01 | Closed | As equipment drawings and data sheets for package have not been issued by vendor till now, final checking of ITP will be done after issuance of above documents. | I see not why equipment drawing and datasheets for package are needed for accepting the ITP. | Noted.
3 | Page 4 | 01 | Closed | W (Hydrostatic test compressor) | It is not possible to visit the compressor manufacturer from Iran. Therefor it is noted as review | Vendor confirmed at bid stage. | Situation is changed from bid stage. Compressor manufacturer is not accepting orders to Iran. So item is as review. | - | Updated to W for thirth party.
4 | Page 5 | 01 | Closed | To be added: -Execution of Major Repairs(if any) (H) -NDT -Check of cleanliness after pressure test | -Execution of Major Repairs(if any) (H): Updated in the next revision -NDT : Updated in the next revision -Check of cleanliness after pressure test: Will be added to the hydrotest procedure, since there is no verifying document for this. This is added as note in the ITP | Noted.
5 | Page 5 | 01 | Closed | +ASME Sec VIII div.1 | Updated accordingly | Noted.
6 | Page 5 | 01 | Closed | To be added as per agreed ITP: -Execution of Major Repairs(if any) (H) -Check of cleanliness after pressure test | -Execution of Major Repairs(if any) (H): Added to the next revision ITP -Check of cleanliness after pressure test: Added as note to the hydrotest. This will be updated in the hydrotest procedure, since there is no verifying document | Noted.
7 | Page 5 | 01 | Closed | routine test and type test of motor shall be carried out based on IEC and also mentioned in the ITP | IEC standard is updated in the next revision | Noted. |  |  |  |  | Open
8 | Page 8 | 01 | Closed | R (Nargan, FAT) | Updated in the next revision | Noted. |  |  |  |  | Closed
9 | Page 8 | 01 | Closed | H (LIDCO, FAT) | Updated in the next revision | "Hold Point" shall be considered for TPI inspector. | Updated in the next revision
10 | Page 9 | 01 | Closed | H (LIDCO, Packing & marking) | Updated in the next revision | "Hold Point" shall be considered for TPI inspector. | Updated in the next revision
11 | Page 9 | 01 | Closed | H (LIDCO, Release of package) | Updated in the next revision | "Hold Point" shall be considered for TPI inspector. | Updated in the next revision
12 | Page 9 | 01 | Closed | Please add documents section: Manufacturing Data Book R, R Non conformity / repairs H, H Deviation / concession request H, H | Updated accordingly | Noted and closed.
Rev.02
13 |  | 02 | Closed | TPA, SW points | Most mentioned points are not possible to witness, such as documents, certificates. All the documents, certificates and reports listed in the ITP can be reviewd in the data book before package release. Therefor TPA points are made R. Furthermore only the compressor hydrotest is witnessed. No other test are witness accoring to the PO. | - | Updated to Hydrotest compressor is witnessed.
14 |  | 02 | Closed | motor type test report to be added | Test not included in PO
15 |  | 02 | Closed | To be added as per agreed ITP: -Execution of Major Repairs(if any) (H) | Added in the next revision
Rev.03
16 |  | 03 | Closed | W (Hydrostatic test compressor) | Updated accordingly
17
18
19
20