## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | 17735-09 Utility Consumption | N-278-VD-6019-GN-UFD-0009-01
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 3 | 1 | Closed | Electrical comment: tag nos to be corrected | Incorporated.
2 | Page 3 | 1 | Closed | Cooling water consumption To be specified. Please clarify what means "TBD". | Incorporated. TBD (To be determent)
3 | Page 3 | 2 | Closed | all electrical user shall be 400 v 3 ph | The oil heating is available only with 230 V / 50Hz, because the power is quite low. Furthermore the oil heating is also already ordered. The 400V / 50 Hz consists normally with 3 phases 230V / 50 Hz. Please check if you can take only 1 phase with 230 V/50 Hz.
4 | Page 3 | 2 | Closed | It should be mentioned in instrument air column | Updated in the next revision
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9
10
11
12
13
14
15
16
17
18