## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Commissioning and Start-up Spares | N-278-VD-6019-GN-OTH-0014-01 17735-13
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 01 | Closed | please mention characteristics of oil in this column | Noted and changed | noted.
2 | 3 | 01 | Closed | please consider separate row for each type and please mention the material of each part. | NA | noted.
3 | 3 | 01 | Closed | Since commissioning spares are based on manufacturer experience, please recheck for the gaskets, bolts/nuts of exchangers and pulsation dampers. | The items mentioned are the items that are sold with this PO. Extra items can be added against extra price. | As per bid stage statement, these are the only item required for stt-up. More items, if required is by vendor.
4 | 3 | 01 | Closed | Please mention in a note that this oil is adequate for one year operation (item 13 of scope of supply) | Yes, it is | Please add mentioned note.
5 | 3 | 01 | Closed | a drawing which includes these parts shall be mentioned | No drawings of O-rings and gasket is applicable | Add GAD drawing no. Please also mention that these gasket and o-ring is related to which item. (for instance oil pump, piping,..,)
6 | 3 | 01 | Closed | model No. to be mentioned here | Noted and changed | noted.
7 | 3 | 01 | Closed | to be corrected based on project tag No. | Corrected into K-020 | noted. |  |  | Open