## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Commissioning and Start-up Spares | N-278-VD-6019-GN-OTH-0014-01 17735-13
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 3 | 02 |  | This column as per below procedure shall be filled. PO number plus three digit serial number, for instance, DXFA0038-001, DXFA0038-002, NXBDO02-001 etc. This number should be tagged to the respective material for easy identification upon receipt at site. | updated
2 | 3 | 02 |  | This column as per below procedure shall be filled. "For classification of Spare Parts: C -for: parts wearing out or deteriorating during normal operation, thus showing fairly regular consumption. Q-for: parts not normally stocked, but -ordered request only. I -for: Insurance items " | updated
3 | 3 | 02 |  | At least GAD drawing to be added. | Included
4 | 3 | 02 |  | As per bid stage agreement 100% o-ring and gasket is required. Please clearly specify the number of o-ring and gasket. 1 set might consist of 10 or more pieces. please provide supportive information here. | all is included in one set.
5 | 3 | 02 |  | For oil, unit shall be changed to litter, and amount of required oil in litter shall be mentioned. | updated.
6 | 3 | 02 |  | Number of installed o-ring and gasket to be specified. | updated with 1. It is one set of all the compressor gaskets. Exact qty. is unknown since it’s a complete set of all under one number
7 | 3 | 02 |  | Purchase order number of main equipment shall be added. | Included |  |  |  | Open