## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | 17735-16 package nameplate | N-278-VD-6019-GN-DWG-0017-01
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 |  | 2 |  | Please mention : -inlet pressure -motor power -Maximum allowable working pressure (MAWP) | Incorporated. The maximum allowable working pressure and the outlet are the same value thats why a combined row is added 'Compressor outlet pressure (MAWP)'
2 |  | 2 |  | Please recheck. in proposal this is RBV-45 | Checked and corrected to RBV-45 this will also be added on P&ID to RBV-45
Open
Closed
20