## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Painting procedure CRS | N-278-VD-6019-GN-PRC-0019-01 (17735-18)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 1 | 1 | Closed | Surface Preparation and Painting Procedure | Incorporated in the next revision | Noted.
2 | Page 3 | 1 | Closed | Remove Colour codes only | Airpack standard paint procedure is followed with the colours of the specification mentioned. | Noted.
3 | Page 3 | 1 | Closed | All carbon and low alloy steel, stainless steel and galvanized steel piping, fittings and valves shall require painting. | It is not possible to paint the grating. Grating paint is easily damaged, therefor it is protected by galvanizing. Stainless steel piping fittings, valves from the paint schedule table is painted. | Stainless steel equipment and piping shall be painted.
4 | Page 4 | 1 | Closed | Vendor shall submit data sheet for different layers of coats in this procedure. | Datasheet is added as attachment to the procedure | Noted.
5 | Page 5 | 1 | Closed | As drawings or data sheets for below mentioned equipment and items has not been issued by vendor, therefore, below table will be checked accordingly. | Table is for the paint and can be checked. | Noted.
Rev. 02
6 | Page 3 | 2 | Closed | With refer clause 9 of Doc. No. N278-000-PI-JSD-2300-005, painting is required for SS equipment. | Sentence is updated accordingly in the next revision. | Noted. |  |  | Open
7 | Page 5 | 2 | Closed | General comment: stainless steel equipments require painting as per project spec. | Table is updated in the next revision | Noted. |  |  | Closed
Rev. 03
8 | Page 6 | 3 |  | Surface preparation of SS materials shall not be as per Sa 21/2. | Updated
9 | Page 6 | 3 |  | 1202 UPC | Updated
10 | Page 6 | 4 |  | Surface preparation of SS materials shall not be as per Sa 21/2. | Updated
11 | Page 6 | 4 |  | 1202 UPC | Updated
12
13
14
15
16
17