## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Index of Vendor Data Book | N-278-VD-6019-GN-LIS-0020-01 (17735-19)
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1
1 | 3 | 2 | CLOSED | Each book shall have page numbers. | Page numbers will be added when the document is complete
2 | 3 | 2 | CLOSED | (N278-000-ME-MR-1020-001) Rev.02 | No problem will be included when the complete book will be made.
3 | 4 | 2 | CLOSED | VDB Part II (Operating and Maintenance Data) has been missed here. It shall contains:  Final Issue of all vendor documents according to approved VPIS by purchaser in PCIM  AFC As-Built Drawings/Vendor Prints  Installation Instruction  Pre-commissioning, Operating Manual and Maintenance Data  Spare parts data including the exploded views and spare parts numbers. All documents shall its own number as per approved VPIS and with final revision numbers. | This is a seperate document. Refer to N-278-VD-6019-GN-LIS-0021-01 for its contents. Will not be included in this document. 1 time is enough.
4 | 4 | 2 | CLOSED | Material summary list and | Yes the summary list is part of the material certificates. We will convert the names of these sections.
5