## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: |  | DOC No:
[5 empty] | Detail Drawings for Pulsation Dampers |  | 17735-23B
Item no. | Reference | Revision | Status | Client Comments | Airpack Reply #1 | Sub supplier Reply #1 | Client Reply #2 | Airpack Reply #2 | Client Reply #2
1 | Page 1 | 00 |  | Type of bolt and required allowable stress in tension/shear to be specified. Please mention bolts are supplied by vendor. |  | Airpack reply: Hexagonal bolt with threath up to the head DIN 933, steel 8.8 you can mention that Airpack will supply this\
2 | Page 1 | 00 |  | General comment for all suppressors: 0 DegC as per purchaser datasheet |  | Noted
3 | Page 1 | 00 |  | As per Elevation view TG and TT should be N3 and N4 |  | Noted
4 | Page 1 | 00 |  | Please clarify from where reference these data is extracted (e.g. ASME B.16.11?) |  | ASME B16,11
5 | Page 1 | 00 |  | Please clarify and indicate in drawing. |  | Tc= throat thickness, typical sketch will be added
6 | Page 1 | 00 |  | Compatibility with other vendor documents including mechanical part document, data sheet,Hook up and purchased instrument is vendor responsibility and scope. this comment include for all pages. | noted | There is no information on documents other than preliminary models Airpack reply: will submit other documents. We are responsible for this
7 | Page 1 | 00 |  | Please clarify why these tests are not considered. please note that these vessels are pulsation dampers and welds should be checked regarding any crack. |  | These tests are not required for Code and not purchased Airpack reply: not included in the order, from sales phase, Considering the very small size of offered package, these loads are negligible and will therefore not be considered. We confirm package design is suitable to withstand such load cases. |  |  |  | Open
8 | Page 1 | 00 |  | General comment for all suppressors: 0 DegC as per purchaser datasheet |  | Noted |  |  |  | Closed
9 | Page 1 | 00 |  | Design code for wind and seismic calculation shall be specified based on MR | Deviation taken, Airpack 23-Aug-2021: Considering the very small size of offered package, these loads are negligible and will therefore not be considered. We confirm package design is suitable to withstand such load cases. | Noted
10 | Page 2 | 00 |  | Please refer to the same comments on page 3. We | noted | Noted
11 | Page 2 | 00 |  | There are discrepancy between N3/N4/N5 |  | Drawing will be alligned
12 | Page 2 | 00 |  | General comments for operating temperature above 65DegC. Please clarify about insulation. | Insulation will be done at Airpack, not at the sub vendor. Insulated parts are shown on the P&ID doc ument. | Noted
13 | Page 3 | 00 |  | Please refer to the same comments on page 3. |  | Noted
14 | Page 4 | 00 |  | Please refer to the same comments on page 3. |  | Noted
15 | Page 2 | 00 |  | As per Elevation view TG and TT should be N3 and N4 |  | Noted
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37