## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Detail Drawings for Pulsation Dampers | 17735-23B
Item no. | Reference | Revision | Status | Client Comments | Airpack Reply #1 | Client Reply #2 | Airpack Reply #2 | Client Reply #2
1 | Page 1 | 00 |  | Type of bolt and required allowable stress in tension/shear to be specified. Please mention bolts are supplied by vendor.
2 | Page 1 | 00 |  | General comment for all suppressors: 0 DegC as per purchaser datasheet
3 | Page 1 | 00 |  | As per Elevation view TG and TT should be N3 and N4
4 | Page 1 | 00 |  | Please clarify from where reference these data is extracted (e.g. ASME B.16.11?)
5 | Page 1 | 00 |  | Please clarify and indicate in drawing.
6 | Page 1 | 00 |  | Compatibility with other vendor documents including mechanical part document, data sheet,Hook up and purchased instrument is vendor responsibility and scope. this comment include for all pages. | noted
7 | Page 1 | 00 |  | Please clarify why these tests are not considered. please note that these vessels are pulsation dampers and welds should be checked regarding any crack. |  |  |  |  | Open
8 | Page 1 | 00 |  | General comment for all suppressors: 0 DegC as per purchaser datasheet |  |  |  |  | Closed
9 | Page 1 | 00 |  | Design code for wind and seismic calculation shall be specified based on MR | Deviation taken, Airpack 23-Aug-2021: Considering the very small size of offered package, these loads are negligible and will therefore not be considered. We confirm package design is suitable to withstand such load cases.
10 | Page 2 | 00 |  | Please refer to the same comments on page 3. We | noted
11 | Page 2 | 00 |  | There are discrepancy between N3/N4/N5
12 | Page 2 | 00 |  | General comments for operating temperature above 65DegC. Please clarify about insulation. | Insulation will be done at Airpack, not at the sub vendor. Insulated parts are shown on the P&ID doc ument.
13 | Page 3 | 00 |  | Please refer to the same comments on page 3.
14 | Page 4 | 00 |  | Please refer to the same comments on page 3.
15 | Page 2 | 00 |  | As per Elevation view TG and TT should be N3 and N4
Rev. 03
16 |  |  |  | Repetitive comment: Please be noted that mentioned document is not found on the VPIS. On VPIS only "Pulsation Study Approach 1 Calculations' is considered which is different from mechanical calculation. Therefore please consider below comment from previous revision. General comment for all drawing: Please note that drawing shall be submitted with calculations. (As per agreements in before order, ASME Sec VIII Div.1 calculation to be submitted. ) So, please attach the calculation to this drawing. If in reviewing the calculation, any change is required, this drawing shall be revised as well. | document is not in the MR of the project. In order to proceed smoothly we have added the calculation | Please be noted that first stage inlet and outlet pulsation damper drawing and calculation can not be found in this document. It seems that second stage pulsation dampers are included in this document twice. Check and add first stage pulsation dampers.
17 |  |  |  | Note and calculation shall be bring back. | this is the latest revision we got from the sub supplier for production | noted.
18 |  |  |  | Repetitive comment: For test ITP shall be followed. | ITP will be leading and followed for tests. Table is as per ITP | noted.
19 |  |  |  | 31 as per data sheet. | Both 2nd stage pulsation dampeners are updated to have the 31L | noted.
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37