## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Detail Drawings for Pulsation Dampers | 17735-23B
Item no. | Reference | Revision | Status | Client Comments | Airpack Reply #1 | Client Reply #2 | Airpack Reply #2 | Client Reply #2
1 | Page 1 | 00 |  | Type of bolt and required allowable stress in tension/shear to be specified. Please mention bolts are supplied by vendor.
2 | Page 1 | 00 |  | General comment for all suppressors: 0 DegC as per purchaser datasheet
3 | Page 1 | 00 |  | As per Elevation view TG and TT should be N3 and N4
4 | Page 1 | 00 |  | Please clarify from where reference these data is extracted (e.g. ASME B.16.11?)
5 | Page 1 | 00 |  | Please clarify and indicate in drawing.
6 | Page 1 | 00 |  | Compatibility with other vendor documents including mechanical part document, data sheet,Hook up and purchased instrument is vendor responsibility and scope. this comment include for all pages. | noted
7 | Page 1 | 00 |  | Please clarify why these tests are not considered. please note that these vessels are pulsation dampers and welds should be checked regarding any crack. |  |  |  |  | Open
8 | Page 1 | 00 |  | General comment for all suppressors: 0 DegC as per purchaser datasheet |  |  |  |  | Closed
9 | Page 1 | 00 |  | Design code for wind and seismic calculation shall be specified based on MR | Deviation taken, Airpack 23-Aug-2021: Considering the very small size of offered package, these loads are negligible and will therefore not be considered. We confirm package design is suitable to withstand such load cases.
10 | Page 2 | 00 |  | Please refer to the same comments on page 3. We | noted
11 | Page 2 | 00 |  | There are discrepancy between N3/N4/N5
12 | Page 2 | 00 |  | General comments for operating temperature above 65DegC. Please clarify about insulation. | Insulation will be done at Airpack, not at the sub vendor. Insulated parts are shown on the P&ID doc ument.
13 | Page 3 | 00 |  | Please refer to the same comments on page 3.
14 | Page 4 | 00 |  | Please refer to the same comments on page 3.
15 | Page 2 | 00 |  | As per Elevation view TG and TT should be N3 and N4
Rev. 03
16 |  |  |  | Repetitive comment: Please be noted that mentioned document is not found on the VPIS. On VPIS only "Pulsation Study Approach 1 Calculations' is considered which is different from mechanical calculation. Therefore please consider below comment from previous revision. General comment for all drawing: Please note that drawing shall be submitted with calculations. (As per agreements in before order, ASME Sec VIII Div.1 calculation to be submitted. ) So, please attach the calculation to this drawing. If in reviewing the calculation, any change is required, this drawing shall be revised as well. | document is not in the MR of the project. In order to proceed smoothly we have added the calculation
17 |  |  |  | Note and calculation shall be bring back. | this is the latest revision we got from the sub supplier for production
18 |  |  |  | Repetitive comment: For test ITP shall be followed. | ITP will be leading and followed for tests. Table is as per ITP
19 |  |  |  | 31 as per data sheet. | Both 2nd stage pulsation dampeners are updated to have the 31L
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37