## Resolution Sheet
|  |  |  | PROJECT: | Integrated Methanol and Ammonia Plant
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Control and shut down Logic Block Diagram | N-278-VD-6019-IN-DIA-0049 (17735-32)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 01 |  | This document will be reviewed again after finalizing control philosophy interlock description document. | Please put the comment in the correct document. For interlock information please refer to Control Philosophy and Cause & Effect chart. | please be informed reference document for this document is "Cause and effect chart" and "Control philosophy and Interlock Description". Compatibility with reference document and other vendor documents is vendor responsibility and scope and next comments are just for hint. Please issue next revision after finalizing "Control philosophy and Interlock Description" document. | There is no need to wait after finalizing the control philosophy since it is our responsibility to keep the documents updated with each other. We will submit the last revision when the order is ready for shipment.
2 | 12 | 01 |  | HS-8204 | Noted. Tag number will be updated. | Noted.
3 | 12 | 01 |  | should be described in control philosophy document too | It is described in the control philosophy in the common alarm and common trip chapter. Accept from DCS will be updated as Acknowledge. | Noted.
4 | 1 | 02 |  | Reference document should be mentioned. - PID Document - Cause and effect chart - Control philosophy and Interlock Description - IO List | Noted. Reference documents will be mentioned.
5 | 2 | 13 |  | Alarm acknowledge | Noted. It will be incorporated.
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20