## report (11)
|  | VENDOR PRINT INDEX & SCHEDULE | [5 empty] | Vendor Logo
[11 empty] | VENDOR |  |  | Airpack (HSE)
LEGEND OF REVIEW CODE
PJT NAME |  | LIDCO Integrated Methanol & Ammonia |  | ISSUE DATE | [6 empty] | CODE 1 : AP : Approved (Released for Manufacturing)
P/O NO. |  | 6019 |  | JOB NO. | N278: | [5 empty] | CODE 2 : : AN : Approved for noted for Fabrication (Fabrication may Proceed)
EQUIPMENT |  |  |  | REQUISITION NO. | [6 empty] | CODE 3 : NF : Approved as Noted for Re-isse (fabrication not Proceed)
NAME | [10 empty] | CODE 4 : RE : Rejected
CODE 5 : NR : Not Returned
S/R NO | DOC. NO. |  | DOCUMENT TITLE |  | Doc. Category | FORECAST DATE | REV.0 |  | REV.1 |  | REV.2 |  | REV.3 |  | REV.4 |  | REV.5 |  | REV.6 |  | REV.7 |  | REV.8 |  | REV.9 |  | REV.10 |  | REV.11 |  | REV.12 |  | REV.13 |  | REV.14 |  | REV.15 |  | REV.16 |  | REV.17 |  | REV.18 |  | REV.19 |  | REV.20 |  | ASBUILT ISSUE DATE | REMARKS
[7 empty] | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW
[7 empty] | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE
1 | N-278-VD-6019-GN-MDR-0001-01 |  | Vendor Print Index and Schedule |  | NA | 2023-07-07 |  |  | 2023-12-04 17:15 | IFA | 2024-01-03 17:34 | IFA | 2024-01-29 13:17 | IFA | 2024-02-28 10:38 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-01 | [7 empty] | 2023-12-10 15:23 | CODE2 | 2024-01-07 16:20 | CODE2 | 2024-02-03 13:58 | CODE2 | 2024-04-02 09:35 | CODE1 | [33 empty] | IFI IFR IFA (As built)
2 | N-278-VD-6019-PR-PID-0002-01 |  | Piping and Instrument Diagram |  | Eng | 2023-07-21 |  |  | 2023-09-14 17:03 | IFA | 2023-11-02 17:16 | IFA | 2023-12-06 18:08 | IFA | 2023-12-15 11:06 | IFA | 2024-01-04 17:34 | IFA | 2024-02-01 16:41 | IFA | 2024-02-13 14:17 | IFA | 2024-03-25 18:20 | IFA | [25 empty] | IFI IFR IFA (As built)
| 17735-03 | [7 empty] | 2023-09-27 09:31 | CODE3 | 2023-11-11 09:27 | CODE3 | 2023-12-12 15:28 | CODE2 | 2023-12-31 09:11 | CODE2 | 2024-01-17 11:19 | CODE2 | 2024-02-10 15:46 | CODE2 | 2024-02-20 15:01 | CODE2 | 2024-04-06 15:26 | CODE1 | [25 empty] | IFI IFR IFA (As built)
3 | N-278-VD-6019-PR-GAD-0003-01 |  | General Arrangement Drawing (incl foundation load details) |  | Eng | 2023-09-29 |  |  | 2024-01-02 13:04 | IFA | 2024-04-17 17:15 | IFA | 2024-06-21 09:42 | IFA | 2024-07-31 12:22 | IFA | 2024-08-28 11:45 | IFA | [31 empty] | IFI IFR IFA (As built)
| 17735-04 | [7 empty] | 2024-01-07 16:08 | CODE2 | 2024-04-30 13:05 | CODE2 | 2024-06-26 17:26 | CODE2 | 2024-08-12 11:46 | CODE2 | 2024-09-07 09:15 | CODE1 | [31 empty] | IFI IFR IFA (As built)
4 | N-278-VD-6019-PR-GAD-0004-01 |  | 3D model (STP) |  | Eng | 2023-09-29 |  |  | 2024-01-02 17:11 | IFA | [39 empty] | IFI IFR IFA (As built)
| 17735-04A | [7 empty] | 2024-01-06 13:42 | CODE1 | [39 empty] | IFI IFR IFA (As built)
5 | N-278-VD-6019-IN-DIA-0005-01 |  | Wiring Diagram (including Terminal Diagram) for LCP Panel and Junction Box |  | Eng | 2023-08-25 |  |  | 2023-11-03 13:01 | IFA | 2023-12-07 17:54 | IFA | 2023-12-21 12:53 | IFA | 2024-02-14 13:56 | IFA | 2024-03-20 12:38 | IFA | 2024-05-02 14:56 | IFA | 2024-05-08 14:37 | IFA | 2024-05-23 10:09 | IFA | [25 empty] | IFI IFR IFA (As built)
| 17735-05 | [7 empty] | 2023-11-11 09:21 | CODE3 | 2023-12-18 08:54 | CODE2 | 2023-12-31 09:36 | CODE2 | 2024-02-21 14:36 | CODE2 | 2024-03-27 16:28 | CODE1 | 2024-05-07 16:20 | CODE2 | 2024-05-14 09:25 | CODE2 | 2024-06-08 09:17 | CODE1 | [25 empty] | IFI IFR IFA (As built)
6 | N-278-VD-6019-IN-LIS-0006-01 |  | I/O List |  | Eng | 2023-08-25 |  |  | 2023-11-10 11:02 | IFA | 2024-02-02 11:20 | IFA | 2024-02-22 11:05 | IFA | 2024-04-05 13:45 | IFA | 2024-04-17 17:15 | IFA | 2024-05-21 13:32 | IFA | 2024-05-30 09:37 | IFA | [27 empty] | IFI IFR IFA (As built)
| 17735-06 | [7 empty] | 2023-11-12 15:44 | CODE3 | 2024-02-10 08:33 | CODE2 | 2024-03-02 08:50 | CODE2 | 2024-04-07 13:41 | CODE2 | 2024-04-27 10:28 | CODE2 | 2024-05-26 16:49 | CODE2 | 2024-06-09 15:49 | CODE1 | [27 empty] | IFI IFR IFA (As built)
7 | N-278-VD-6019-IN-DWG-0007-01 |  | Outline Dimensional Drawings for LCP Panel and Junction Box |  | Eng | 2023-09-22 |  |  | 2023-12-07 17:58 | IFA | 2023-12-21 12:55 | IFA | 2024-02-14 13:57 | IFA | 2024-03-20 12:38 | IFA | 2024-04-18 13:14 | IFA | 2024-05-02 14:56 | IFA | [29 empty] | IFI IFR IFA (As built)
| 17735-07 | [7 empty] | 2023-12-18 08:56 | CODE2 | 2023-12-31 09:33 | CODE2 | 2024-02-21 14:29 | CODE2 | 2024-03-27 16:28 | CODE2 | 2024-04-27 10:04 | CODE2 | 2024-05-07 16:20 | CODE1 | [29 empty] | IFI IFR IFA (As built)
8 | N-278-VD-6019-GN-ITP-0008-01 |  | Inspection and Test Plan (ITP) |  | NA | 2023-07-21 |  |  | 2023-09-14 17:07 | IFA | 2023-11-13 15:13 | IFA | 2024-04-03 17:54 | IFA | 2024-04-09 17:55 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-08 | [7 empty] | 2023-09-25 07:36 | CODE2 | 2023-11-22 08:27 | CODE2 | 2024-04-09 13:53 | CODE1 | 2024-04-17 10:37 | CODE1 | [33 empty] | IFI IFR IFA (As built)
9 | N-278-VD-6019-GN-UFD-0009-01 |  | Utility Consumption |  | Eng | 2023-08-11 |  |  | 2023-09-14 17:10 | IFA | 2024-01-29 13:59 | IFA | 2024-03-25 18:20 | IFA | [35 empty] | IFI IFR IFA (As built)
| 17735-09 | [7 empty] | 2023-09-23 08:22 | CODE2 | 2024-02-04 11:42 | CODE2 | 2024-04-06 15:26 | CODE1 | [35 empty] | IFI IFR IFA (As built)
10 | N-278-VD-6019-PM-DS-0010-01 |  | Main Motor Data Sheet |  | Eng | 2023-08-11 |  |  | 2024-04-08 17:16 | IFA | 2024-06-03 16:58 | IFA | 2024-06-10 14:40 | IFA | 2024-06-21 09:42 | IFA | 2024-07-01 17:45 | IFA | 2024-07-03 14:28 | IFA | [29 empty] | IFI IFR IFA (As built)
| 17735-10 | [7 empty] | 2024-04-20 08:50 | CODE2 | 2024-06-09 08:39 | CODE2 | 2024-06-19 16:58 | CODE2 | 2024-06-26 17:26 | CODE2 | 2024-07-02 16:28 | CODE2 | 2024-07-20 08:55 | CODE1 | [29 empty] | IFI IFR IFA (As built)
11 | N-278-VD-6019-ME-DS-0011-01 |  | Equipment Data Sheet |  | Eng | 2023-09-01 |  |  | 2024-04-08 13:42 | IFA | 2024-06-10 14:40 | IFA | 2024-06-27 10:14 | IFA | 2024-07-23 11:44 | IFA | 2024-08-07 10:06 | IFA | 2024-09-16 13:31 | IFA | 2024-10-18 12:22 | IFA | [27 empty] | IFI IFR IFA (As built)
| 17735-11A | [7 empty] | 2024-04-20 08:52 | CODE3 | 2024-06-19 16:58 | CODE3 | 2024-07-02 16:26 | CODE2 | 2024-08-03 15:39 | CODE2 | 2024-08-14 10:45 | CODE2 | 2024-09-24 09:35 | CODE2 | 2024-10-19 15:42 | CODE2 | [27 empty] | IFI IFR IFA (As built)
12 | N-278-VD-6019-ME-DS-0012-01 |  | Inter / After Cooler Data Sheet |  | Eng | 2023-09-01 |  |  | 2024-04-03 17:54 | IFA | 2024-06-12 15:51 | IFA | 2024-06-20 10:15 | IFA | 2024-07-01 17:45 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-11B | [7 empty] | 2024-04-14 12:41 | CODE2 | 2024-06-18 11:22 | CODE2 | 2024-06-29 15:08 | CODE2 | 2024-07-02 16:28 | CODE1 | [33 empty] | IFI IFR IFA (As built)
13 | N-278-VD-6019-IN-DS-0013-01 |  | Instrument Data Sheet |  | Eng | 2023-09-01 |  |  | 2023-11-09 15:33 | IFA | 2023-12-15 11:19 | IFA | 2024-03-11 13:01 | IFA | 2024-04-17 17:15 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-12 | [7 empty] | 2023-11-21 14:45 | CODE2 | 2023-12-24 10:31 | CODE2 | 2024-03-24 09:36 | CODE2 | 2024-04-27 10:28 | CODE2 | [33 empty] | IFI IFR IFA (As built)
14 | N-278-VD-6019-GN-OTH-0014-01 |  | Commissioning and Start-up Spares |  | Eng | 2023-07-28 |  |  | 2023-09-15 12:09 | IFI | [39 empty] | IFI IFR IFA (As built)
| 17735-13 | [7 empty] | 2023-09-23 08:54 | CODE2 | [39 empty] | IFI IFR IFA (As built)
15 | N-278-VD-6019-GN-PRC-0015-01 |  | FAT Procedure (incl full unit mechanical run test procedure) |  | NA | 2023-08-11 |  |  | 2023-09-15 11:45 | IFA | 2024-01-03 15:49 | IFA | 2024-01-31 13:29 | IFA | 2024-03-25 14:00 | IFA | 2024-04-09 17:55 | IFA | 2024-06-10 14:40 | IFA | [29 empty] | IFI IFR IFA (As built)
| 17735-14 | [7 empty] | 2023-10-07 09:37 | CODE2 | 2024-01-07 16:36 | CODE2 | 2024-02-10 08:37 | CODE2 | 2024-04-06 15:27 | CODE2 | 2024-04-20 08:48 | CODE2 | 2024-06-22 13:42 | CODE2 | [29 empty] | IFI IFR IFA (As built)
16 | N-278-VD-6019-GN-PRC-0016-01 |  | NDE Procedure |  | NA | 2023-08-11 |  |  | 2023-12-14 13:53 | IFA | 2024-03-20 17:59 | IFA | [37 empty] | IFI IFR IFA (As built)
| 17735-15 | [7 empty] | 2023-12-16 08:08 | CODE2 | 2024-04-02 12:21 | CODE1 | [37 empty] | IFI IFR IFA (As built)
17 | N-278-VD-6019-GN-DWG-0017-01 |  | Package Nameplate Drawing |  | Eng | 2023-10-11 |  |  | 2023-09-15 11:18 | IFA | 2024-01-16 15:22 | IFA | 2024-01-24 14:24 | IFA | 2024-01-29 13:44 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-16 | [7 empty] | 2023-09-23 08:31 | CODE2 | 2024-01-21 08:41 | CODE2 | 2024-01-28 08:24 | CODE2 | 2024-01-29 13:50 | CODE1 | [33 empty] | IFI IFR IFA (As built)
18 | N-278-VD-6019-GN-PRC-0018-01 |  | Hydrotest Procedure |  | NA | 2023-08-25 |  |  | 2023-09-14 17:56 | IFA | 2023-11-06 15:27 | IFA | 2023-12-11 15:58 | IFA | 2023-12-13 10:06 | IFA | 2023-12-18 18:42 | IFA | 2024-04-18 13:14 | IFA | [29 empty] | IFI IFR IFA (As built)
| 17735-17 | [7 empty] | 2023-09-18 09:26 | CODE2 | 2023-11-07 14:40 | CODE2 | 2023-12-13 08:31 | CODE1 | 2023-12-16 10:21 | CODE2 | 2023-12-23 11:53 | CODE2 | 2024-04-28 09:09 | CODE2 | [29 empty] | IFI IFR IFA (As built)
19 | N-278-VD-6019-GN-PRC-0019-01 |  | Surface Preparation and Painting Procedure |  | Eng | 2023-08-25 |  |  | 2023-09-14 17:44 | IFA | 2023-12-11 15:44 | IFA | 2024-04-08 13:42 | IFA | 2024-04-09 17:55 | IFA | 2024-05-23 10:09 | IFA | [31 empty] | IFI IFR IFA (As built)
| 17735-18 | [7 empty] | 2023-09-19 09:23 | CODE2 | 2023-12-16 10:43 | CODE2 | 2024-04-09 10:06 | CODE2 | 2024-04-17 10:37 | CODE2 | 2024-10-19 09:21 | CODE1 | [31 empty] | IFI IFR IFA (As built)
20 | N-278-VD-6019-GN-LIS-0020-01 |  | Index of Vendor Data Book |  | NA | 2023-09-04 |  |  | 2023-11-13 16:18 | IFA | 2023-12-19 16:37 | IFA | 2024-02-06 13:24 | IFA | [35 empty] | IFI IFR IFA (As built)
| 17735-19 | [7 empty] | 2023-11-18 13:35 | CODE2 | 2023-12-23 11:50 | CODE2 | 2024-02-06 14:40 | CODE1 | [35 empty] | IFI IFR IFA (As built)
21 | N-278-VD-6019-GN-LIS-0021-01 |  | Index of Instruction and Operating Manual |  | Eng | 2023-09-20 |  |  | 2023-11-13 16:19 | IFA | 2023-12-13 13:53 | IFA | 2024-02-06 13:05 | IFA | 2024-02-14 12:05 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-20 | [7 empty] | 2023-11-21 14:40 | CODE2 | 2023-12-23 11:55 | CODE2 | 2024-02-10 14:40 | CODE2 | 2024-02-19 13:57 | CODE1 | [33 empty] | IFI IFR IFA (As built)
22 | N-278-VD-6019-GN-PRO-0022-01 |  | Control philosophy and Interlock Description |  | Eng | 2023-08-25 |  |  | 2023-12-12 15:42 | IFA | 2024-05-01 10:55 | IFA | 2024-06-11 09:47 | IFA | 2024-06-25 09:34 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-21 | [7 empty] | 2023-12-20 14:59 | CODE2 | 2024-05-11 10:38 | CODE2 | 2024-06-22 10:56 | CODE2 | 2024-07-01 11:12 | CODE1 | [33 empty] | IFI IFR IFA (As built)
23 | N-278-VD-6019-GN-PRC-0023-01 |  | Preservation, Packing and Shipping Procedure |  | NA | 2023-08-22 |  |  | 2023-12-05 10:53 | IFA | 2024-01-04 17:33 | IFA | 2024-01-15 18:11 | IFA | 2024-02-01 17:40 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-22 | [7 empty] | 2023-12-06 15:04 | CODE2 | 2024-01-08 11:17 | CODE2 | 2024-01-17 09:13 | CODE2 | 2024-02-06 09:33 | CODE1 | [33 empty] | IFI IFR IFA (As built)
24 | N-278-VD-6019-ME-DWG-0024-01 |  | Detail Drawings for Coolers |  | Eng | 2023-09-15 |  |  | 2023-12-13 15:53 | IFA | 2024-02-12 12:18 | IFI | 2024-04-25 18:42 | IFI | 2024-05-08 09:07 | IFI | 2024-05-21 13:32 | IFI | [31 empty] | IFI IFR IFA (As built)
| 17735-23A | [7 empty] | 2023-12-23 11:08 | CODE3 | 2024-02-21 14:19 | CODE3 | 2024-05-01 12:48 | CODE2 | 2024-05-11 10:08 | CODE2 | 2024-05-26 16:49 | CODE1 | [31 empty] | IFI IFR IFA (As built)
25 | N-278-VD-6019-ME-DWG-0025-01 |  | Detail Drawings for Pulsation Dampers |  | Eng | 2023-09-15 |  |  | 2024-02-21 16:04 | IFA | 2024-05-15 12:58 | IFA | 2024-09-16 13:31 | IFA | 2024-10-15 11:16 | IFA | 2024-10-21 10:27 | IFA | [31 empty] | IFI IFR IFA (As built)
| 17735-23B | [7 empty] | 2024-03-06 08:37 | CODE2 | 2024-05-20 15:20 | CODE2 | 2024-09-24 09:35 | CODE2 | 2024-10-19 13:59 | CODE2 | 2024-10-21 14:49 | CODE2 | [31 empty] | IFI IFR IFA (As built)
26 | N-278-VD-6019-ME-CAL-0026-01 |  | Pulsation Study Approach 1 Calculations |  | Eng | 2023-09-15 |  |  | 2023-09-14 17:21 | IFI | 2023-12-13 17:39 | IFI | 2024-06-20 10:15 | IFI | 2024-07-15 14:22 | IFI | 2024-08-02 10:23 | IFI | [31 empty] | IFI IFR IFA (As built)
| 17735-24 | [7 empty] | 2023-09-23 08:25 | CODE3 | 2023-12-20 16:35 | CODE2 | 2024-06-29 15:08 | CODE2 | 2024-07-22 14:45 | CODE2 | 2024-08-04 13:20 | CODE1 | [31 empty] | IFI IFR IFA (As built)
27 | N-278-VD-6019-GN-WS-0027-01 |  | Welding Book (PQR / WPS) |  | NA | 2023-08-25 |  |  | 2023-12-12 13:38 | IFI | 2024-03-21 17:11 | IFI | 2024-04-19 10:26 | IFI | [35 empty] | IFI IFR IFA (As built)
| 17735-25 | [7 empty] | 2023-12-27 10:50 | CODE2 | 2024-04-03 11:08 | CODE2 | 2024-04-21 12:14 | CODE1 | [35 empty] | IFI IFR IFA (As built)
28 | N-278-VD-6019-GN-WS-0028-01 |  | WPQ |  | NA | 2023-08-25 |  |  | 2023-12-12 13:45 | IFI | [39 empty] | IFI IFR IFA (As built)
| 17735-26 | [7 empty] | 2023-12-13 11:05 | CODE1 | [39 empty] | IFI IFR IFA (As built)
29 | N-278-VD-6019-GN-SF-0029-01 |  | Cause and Effect Chart |  | Eng | 2023-09-08 |  |  | 2023-12-12 13:49 | IFA | 2024-05-23 10:09 | IFA | 2024-06-11 17:45 | IFA | 2024-06-25 09:34 | IFA | 2024-07-05 13:03 | IFA | 2024-07-18 10:14 | IFA | 2024-07-29 16:56 | IFA | [27 empty] | IFI IFR IFA (As built)
| 17735-27 | [7 empty] | 2023-12-20 14:41 | CODE2 | 2024-06-08 09:17 | CODE2 | 2024-06-22 10:56 | CODE2 | 2024-07-01 11:12 | CODE2 | 2024-07-10 12:36 | CODE2 | 2024-07-27 10:29 | CODE2 | 2024-08-03 15:40 | CODE1 | [27 empty] | IFI IFR IFA (As built)
30 | N-278-VD-6019-GN-OTH-0030-01 |  | Tie-in Nozzle Loads |  | Eng | 2023-10-10 |  |  | 2023-12-11 15:38 | IFI | 2023-12-14 13:56 | IFI | [37 empty] | IFI IFR IFA (As built)
| 17735-28 | [7 empty] | 2023-12-12 14:32 | CODE2 | 2023-12-16 13:24 | CODE1 | [37 empty] | IFI IFR IFA (As built)
31 | N-278-VD-6019-EL-DIA-0031-01 |  | Loop Diagrams |  | Eng | 2023-09-22 |  |  | 2023-12-07 18:01 | IFA | 2023-12-21 12:55 | IFA | 2024-02-14 13:58 | IFA | 2024-03-20 12:38 | IFA | 2024-04-18 13:14 | IFA | 2024-05-02 14:56 | IFA | 2024-05-08 14:37 | IFA | 2024-05-23 10:09 | IFA | [25 empty] | IFI IFR IFA (As built)
| 17735-30 | [7 empty] | 2023-12-12 15:09 | CODE3 | 2023-12-31 09:30 | CODE2 | 2024-02-27 08:27 | CODE2 | 2024-03-27 16:28 | CODE2 | 2024-04-27 10:04 | CODE2 | 2024-05-07 16:20 | CODE2 | 2024-05-14 09:25 | CODE2 | 2024-06-08 09:17 | CODE1 | [25 empty] | IFI IFR IFA (As built)
32 | N-278-VD-6019-EL-DIA-01 |  | Control and shut down Logic Block Diagram |  | Eng | 2023-11-22 |  |  | 2024-03-08 13:57 | IFA | 2024-04-09 17:55 | IFA | 2024-05-01 16:21 | IFA | 2024-07-05 13:03 | IFA | 2024-07-18 14:54 | IFA | 2024-08-06 14:48 | IFA | 2024-08-27 15:48 | IFA | [27 empty] | IFI IFR IFA (As built)
| 17735-32 | [7 empty] | 2024-03-16 09:09 | CODE2 | 2024-04-20 08:48 | CODE2 | 2024-05-07 08:53 | CODE2 | 2024-07-10 12:36 | CODE2 | 2024-07-27 10:30 | CODE2 | 2024-08-07 10:57 | CODE2 | 2024-08-31 14:21 | CODE1 | [27 empty] | IFI IFR IFA (As built)
33 | N-278-VD-6019-GN-PRC-0032-01 |  | (Pre-) Commissioning Procedure |  | Eng | 2023-09-15 |  |  | 2024-04-19 17:24 | IFA | 2024-05-21 13:32 | IFA | [37 empty] | IFI IFR IFA (As built)
| 17735-33 | [7 empty] | 2024-05-05 15:10 | CODE2 | 2024-05-26 16:49 | CODE1 | [37 empty] | IFI IFR IFA (As built)
34 | N-278-VD-6019-IN-LIS-0033-01 |  | Instrument Index |  | Eng | 2023-09-15 |  |  | 2023-11-09 17:19 | IFA | 2024-04-18 13:14 | IFA | 2024-05-21 13:32 | IFA | 2024-05-30 09:37 | IFA | [33 empty] | IFI IFR IFA (As built)
| 17735-35 | [7 empty] | 2023-11-13 15:29 | CODE3 | 2024-04-27 10:04 | CODE2 | 2024-05-26 16:49 | CODE2 | 2024-06-09 15:49 | CODE1 | [33 empty] | IFI IFR IFA (As built)
35 | N-278-VD-6019-GN-MNL-0034-01 |  | Quality Manual |  | NA | 2023-08-04 |  |  | 2023-11-28 18:16 | IFI | [39 empty] | IFI IFR IFA (As built)
| 17735-37 | [48 empty] | IFI IFR IFA (As built)
36 | N-278-VD-6019-IN-DWG-0035-01 |  | Instrument Hook-up Drawing |  | NA | 2023-08-04 |  |  | 2023-12-07 16:21 | IFA | 2024-02-14 11:39 | IFA | 2024-03-18 18:25 | IFA | [35 empty] | IFI IFR IFA (As built)
| 17735-38 | [7 empty] | 2023-12-23 08:53 | CODE2 | 2024-02-21 09:44 | CODE2 | 2024-03-26 17:01 | CODE1 | [35 empty] | IFI IFR IFA (As built)
37 | N-278-VD-6019-EL-DIA-0036-01 |  | Earthing Diagrams |  | Eng | 2023-09-22 |  |  | 2023-11-28 18:20 | IFA | 2024-03-11 13:01 | IFA | [37 empty] | IFI IFR IFA (As built)
| 17735-41 | [7 empty] | 2023-12-03 09:37 | CODE2 | 2024-03-24 09:36 | CODE1 | [37 empty] | IFI IFR IFA (As built)
38 | N-278-VD-6019-GN-OTH-0037-01 |  | Spare Parts for 2 years Operation (SPIR) |  | Eng | 2023-12-29 | [43 empty] | IFI IFR IFA (As built)
| 17735-42 | [48 empty] | IFI IFR IFA (As built)
39 | N-278-VD-6019-GN-EQL-0038-01 |  | Sub-Supplier List |  | NA | 2023-08-04 |  |  | 2023-09-14 10:24 | IFA | 2023-11-28 18:17 | IFA | 2023-12-04 17:14 | IFA | [35 empty] | IFI IFR IFA (As built)
| 17735-43 | [7 empty] | 2023-09-23 12:51 | CODE3 | 2023-12-03 12:49 | CODE2 | 2023-12-05 14:24 | CODE1 | [35 empty] | IFI IFR IFA (As built)
40 | N-278-VD-6019-IN-DS-0039-01 |  | PSV Data Sheets |  | Eng | 2023-09-22 |  |  | 2023-11-08 17:26 | IFA | 2024-03-11 13:01 | IFA | 2024-03-26 19:53 | IFA | 2024-04-17 17:15 | IFA | 2024-05-08 12:15 | IFA | 2024-06-25 17:01 | IFA | [29 empty] | IFI IFR IFA (As built)
| 17735-46 | [7 empty] | 2023-11-21 14:44 | CODE2 | 2024-03-24 09:36 | CODE2 | 2024-04-07 17:02 | CODE2 | 2024-04-27 10:28 | CODE2 | 2024-05-15 16:58 | CODE2 | 2024-07-01 14:47 | CODE1 | [29 empty] | IFI IFR IFA (As built)
41 | N-278-VD-6019-IN-CAL-0040-01 |  | PSV sizing calculations |  | Eng | 2023-12-15 |  |  | 2024-05-08 12:15 | IFA | 2024-06-25 17:01 | IFA | [37 empty] | IFI IFR IFA (As built)
| 17735-47 | [7 empty] | 2024-05-15 16:58 | CODE2 | 2024-07-01 14:47 | CODE1 | [37 empty] | IFI IFR IFA (As built)
42 | N-278-VD-6019-IN-DS-0041-01 |  | Control Valve Data Sheet |  | Eng | 2023-09-22 |  |  | 2023-11-09 15:35 | IFA | 2024-03-11 13:01 | IFA | 2024-04-17 17:15 | IFA | 2024-05-23 10:09 | IFA | 2024-07-08 12:37 | IFA | 2024-08-01 11:50 | IFA | 2024-09-05 10:08 | IFA | 2024-09-16 13:31 | IFA | [25 empty] | IFI IFR IFA (As built)
| 17735-48 | [7 empty] | 2023-11-25 10:26 | CODE2 | 2024-04-06 15:24 | CODE2 | 2024-04-27 10:28 | CODE2 | 2024-06-08 09:17 | CODE2 | 2024-07-17 14:03 | CODE2 | 2024-08-12 16:02 | CODE2 | 2024-09-10 14:58 | CODE2 | 2024-09-24 09:35 | CODE1 | [25 empty] | IFI IFR IFA (As built)
43 | N-278-VD-6019-IN-DS-0042-01 |  | Noise Data Sheet |  | Eng | 0000-00-00 00:00:00 | [43 empty] | IFI IFR IFA (As built)
| 17735-49 | [48 empty] | IFI IFR IFA (As built)
44 | N-278-VD-6019-PR-LIS-0043-01 |  | Lubrication List |  | Eng | 2023-09-29 |  |  | 2023-09-14 17:41 | IFA | 2024-01-30 10:52 | IFA | 2024-04-17 17:15 | IFA | [35 empty] | IFI IFR IFA (As built)
| 17735-51 | [7 empty] | 2023-09-23 08:28 | CODE2 | 2024-02-03 10:45 | CODE2 | 2024-04-30 13:05 | CODE1 | [35 empty] | IFI IFR IFA (As built)
45 | N-278-VD-6019-IN-SCH-0044-01 |  | Instrument Cable Schedule |  | Eng | 2023-09-29 |  |  | 2023-12-13 17:17 | IFA | 2024-02-15 18:14 | IFA | 2024-03-20 12:38 | IFA | 2024-04-03 17:54 | IFA | 2024-05-02 14:56 | IFA | 2024-05-08 14:37 | IFA | 2024-05-23 10:09 | IFA | [27 empty] | IFI IFR IFA (As built)
| 17735-52 | [7 empty] | 2023-12-20 16:22 | CODE2 | 2024-02-21 14:21 | CODE2 | 2024-03-27 16:28 | CODE2 | 2024-04-14 12:41 | CODE1 | 2024-05-07 16:20 | CODE2 | 2024-05-14 09:25 | CODE2 | 2024-06-08 09:17 | CODE1 | [27 empty] | IFI IFR IFA (As built)
46 | N-278-VD-6019-GN-MNL-0045-01 |  | Vendor Data book |  | NA | 0000-00-00 00:00:00 | [43 empty] | IFI IFR IFA (As built)
| 17735-58 | [48 empty] | IFI IFR IFA (As built)
47 | N-278-VD-6019-GN-MNL-0046-01 |  | Technical Operating and Maintenance Manual |  | Eng | 0000-00-00 00:00:00 | [43 empty] | IFI IFR IFA (As built)
| 17735-59 | [48 empty] | IFI IFR IFA (As built)
48 | N-278-VD-6019-GN-MRP-0047-01 |  | Monthly Progress Report |  | Eng | 0000-00-00 00:00:00 |  |  | 2023-11-17 14:29 | IFI | 2024-08-07 10:06 | IFI | 2024-11-26 13:27 | IFI | [35 empty] | IFI IFR IFA (As built)
| 17735-60 | [7 empty] | 2023-11-25 13:24 | CODE2 | 2024-09-01 11:27 | CODE3 | [37 empty] | IFI IFR IFA (As built)
49 | N-278-VD-6019-IN-LIS-0048-01 |  | Line List |  | Eng | 2023-09-29 |  |  | 2023-12-19 13:24 | IFA | 2024-01-08 09:52 | IFA | 2024-01-23 14:01 | IFA | 2024-04-08 13:42 | IFA | 2024-04-26 12:46 | IFA | [31 empty] | IFI IFR IFA (As built)
| 17735-61 | [7 empty] | 2023-12-23 11:10 | CODE3 | 2024-01-16 13:29 | CODE2 | 2024-01-29 13:33 | CODE2 | 2024-04-20 08:52 | CODE2 | 2024-05-06 09:15 | CODE1 | [31 empty] | IFI IFR IFA (As built)
50 | IN-278-6019 |  | Inspection Notification |  | NA | 0000-00-00 00:00:00 |  |  | 2024-04-09 18:01 | IFI | 2024-12-16 15:20 | IFI | 2024-12-17 13:13 | IFI | 2024-12-17 15:34 | IFI | [33 empty] | IFI IFR IFA (As built)
| 17735-62 | [7 empty] | 2024-04-13 15:54 | CODE3 | 2024-12-16 15:28 | CODE3 | 2024-12-17 13:35 | CODE3 | [35 empty] | IFI IFR IFA (As built)