## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 05/Oct/2020 | Rev.:
|  | Comment Sheet Ref.No.: | Doc Description: GENERAL ARRANGEMENT DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00031 | Doc. No.: BU-20-VD-303-ME-DWG-0076
|  | Transmittal Date: 06/10/2021 | Doc Rev.: 05
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CHCE Reply | Vendor reply #2
1 | Coordinate of instruments and JBs location (X,Y,Z) regarding to base point shall be specified. |  |  | JB, coordinate table is included. Instruments are indicated with identification nr. |  |  | Noted, but instrument coordination to be added too. | Instrument coordinated will not be included, all instruments can be found by indentification numbers.
2 | Cable tray routing shall be specified. |  |  | Cable tray routing will not be indicated on this document |  |  | Please specify in which document will be indicate. | Cable tie-in points are indicated, cable tray routing to juncition boxes is indicated. Internal cable trays will not be included on GA.
3 | Cable tray cross section shall be specified. |  |  | Cable tray cross section will not be indicated on this document |  |  | Please specify in which document will be indicate. | 50x50mm cable trays are used.
4 | Please modify COG dimension. |  |  | noted and updated
5 | EL.02: Earth lugs shall be suitable to be connect to the earth cable 70mm. |  |  | noted, earthluggs suitable for M10 and 70mm² cable
6 | EL.01: Specify exact place of earth lugs in the drawing. |  |  | Indicated on drawing
7 | Compressor information table including motor data |  |  | Refer to P&ID for compressor information details |  |  | Some general data same as p&id need to be added to this dociment. Such as tag number, motor power, compressor cappacity | Noted an included CES REPLY: Closed.
8 | 1-Please specify operational frequency of compressor in this drawing. |  |  | Noted, frequency is indicated
9 | Maintenance part and weight to be added |  |  | maintenance weights are indicated
10 | 1- Please add skid weigh 2- Please add whole compressor package weight. |  |  | 1. Skid weight is included 2. Package weight 3000 kg allready indicated
11 | Instrument Air |  |  | noted
12 | Considering the fact that 1 1/2" is met the criteria. Please check if 1 1/2" can be used. |  |  | 2" according P&ID is used
13 | Please refer to comment on page 2 of P&ID |  |  | noted and updated
14 | Tag numbers must be consistent with Tag numbers in PID. |  |  | noted and updated
15 | All modifications shall be shown cloudy with revision mark. |  |  | noted and included
16 | Prerequisite document such as wiring diagram and instrument index to be issued before this document. |  |  | Documentts will be send according document schedule.
17 | Repeated Comment - Coordinate of instruments location (X,Y,Z) regarding to base point shall be specified. - Cable tray routing shall be specified. - Cable tray cross section shall be specified. |  |  | Refer to item 2, 4 and 5 above
18 | REPITEDED CLIENT COMMENT: Please add: - Compressor information table including motor data |  |  | Noted. information table is included
19 | If this is base point please specify in the legend? |  |  | Base point symbol added with discription
20 | ? |  |  | Dimensions indicated
21 | Please refer to comment on page 2 of P&ID |  |  | JB nr updated.
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56