## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 09/11/2021 | Rev.: 00
|  | Comment Sheet Ref.No.: | Doc Description: Surface preparation & painting procedure
|  | Transmittal No.: APCES-V-00047 | Doc. No.: BU-20-VD-303-PI-DCR-0010
|  | Transmittal Date: 09/11/2021 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | With reference to clause PI2 of TCL, RAL number shall be as per project requirement. Therefor RAL number shall be RAL-7035 |  |  | This is special paint which does not come in any specific color, just Aluminium finish, so we cannot change the RAL color. CES REPLY (Nov.16,2021): vendor's justification about RAL No. is not convincing, because final color of paint system 3 for Pulsation Damper, Compressor and PSV is 7035, but same final color can not be applied for the rest parts painted by painting system 3, please clarify.
2 | Aluminium - RAL 9006 |  |  | This is special paint which does not come in any specific color, just Aluminium finish, so we cannot change the RAL color. CES REPLY (Nov.16,2021): Please technically clarify why RAL 9006 is not applicable.