## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 06/Apr/2022 | Rev.:03
|  | Comment Sheet Ref.No.: | Doc Description: MECHANICAL DATA SHEET FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00120 | Doc. No.: BU-20-VD-303-ME-DSH-0022
|  | Transmittal Date: 06/Apr/2022 | Doc Rev.: 03
Item | CHCE Comment |  |  | Vendor Clarification
1 | LEVELING SCREWS, SUB SOLE PLATES, CHOKE BLOCKS and shims are required. |  |  | Not required for mounting on a foundation, this will be mounted with anchor bolts, levelling is not required. CES REPLY (Dec.18,2021): It is in AIRPACK responsibility to consider all required facilities for safe and reliable installation of compressor. Noted and closed
2 | With reference to clause 6.1.7 of API618 5th edition, allowable pressure drop along heat exchanger shall not exceed 1bar. Also with reference to clause 4.3.6 of BU-20-D-000-PR-SPC-101-06 pressure unit is bara. |  |  | pressure drop accros the cooler is as per pressure drop stated in the the information from client, additional pressure drop is created by a globe valve in the cooling water line to the cooler. Unit is bar(g) as per P&ID CES REPLY (Dec.18,2021): Closed.
3 | 1- ASTM material equivalent shall be added. |  |  | will not be added, as this are the materials used CES REPLY (Dec.18,2021): Closed. But base material of mentioned component shall be specified.
4 | All remaining data to be completed |  |  | After completion of pulsation study, currently waiting for customer piping details CES REPLY (Dec.18,2021): We are waiting to receive new data. Added
5 | All Notes shall be revised as per attached file. |  |  | This is what was provided in this format CES REPLY (Dec.18,2021): Notes in page 20 of BU-20-VD-303-ME-DSH-0022 are related to instrument air compressor. Therefor, notes shall be revised as per attached file. See TCL Clause M33.Added
6 | Compressor is V-BELT |  |  | updated CES reply (Mar. 16,2022): Closed.
7 | How it is possible to provide liner with 48 mm thickness for cylinder with 160mm??????? |  |  | because compressor is suitable for much larger piston CES reply (Mar. 16,2022): Closed.
8 | Size shall be added. 1'', 2'', 3''..... |  |  | updated CES reply (Mar. 16,2022): Closed.
9 | Please check it again |  |  | checked and confirmed CES reply (Mar. 16,2022): Closed.
10 | These notes shall be revised as per attached file. |  |  | updated CES reply (Mar. 16,2022): Closed.
1. | Both stage condition shall be written. |  |  | In the datasheet it is mentioned as operating condition (each machine), not each stage, therefore will not be added CES REPLY: With reference to annex A of API 618 5th edition, stage number shall be added. Therefor, one line shall be insert after row 15 to show stage number and all operating condition of each stage shall be specified separatly.
2. | Please specify the base material |  |  | Not possile as it is a combination of materials, PTFE with carbon for example CES reply: Please add combination material. I have to know what the material is.
3. | Please specify piston rod hardness material. |  |  | Is already specified? CES reply: Hardness material is not specified yet. I mean something like "AISI 630 / 29 HRC"
4. | Please specify the base material |  |  | Not possile as it is a combination of materials, PTFE with carbon for example CES reply: Please add combination material. I have to know what the material is.
5. | Please specify the base material |  |  | Not possile as it is a combination of materials, PTFE with carbon for example CES reply: Please add combination material. I have to know what the material is.
6. | Please specify the base material |  |  | Not possile as it is a combination of materials, PTFE with carbon for example CES reply: Please add combination material. I have to know what the material is.
7. | Considering 0.018 bara pressure drop through pulsation dampener, 11.2% is not correct shall be changed into 0.2%. |  |  | there were som things swapped, has been update corectly. CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
8. | Considering 0.15 bara pressure drop through pulsation dampener, 35.2% is not correct shall be changed into 1% |  |  | there were som things swapped, has been update corectly CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
9. | With reference clause 7.9.4.2.5.2.1 of API 618 5th edition, Pcf= 3xR % which shall be less than 7%. Therefore, 54.3% and 103.3% are not correct and shall be revised. |  |  | Notation was different, has been updated CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
10. | Please check the pressure again considering that allowable PEAK-PEAK shall be less than 7%. |  |  | updated CES reply: Closed.
11. | Based on comment on pulsation dampener data sheet, capacity shall be 100 Lit. |  |  | based on actual calculation, so not changed CES reply: See latest comments on pulsation dampener data sheet as well as clause 7.9.3.2 of API 618 5th edition.
12. | Please check these again considering ALLOWABLE PRESSURE DROP THROUGH SUPPRESSORS. |  |  | there were som things swapped, has been update corectly CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
13. | Considering 0.0636 pressure drop through pulsation dampener, 52% is not correct shall be changed into 0.41% |  |  | there were som things swapped, has been update corectly CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
| Considering 0.06 pressure drop through pulsation dampener, 41% is not correct shall be changed into 0.25% |  |  | there were som things swapped, has been update corectly CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
| With reference clause 7.9.4.2.5.2.1 of API 618 5th edition, Pcf= 3xR % which shall be less than 7%. Therefore, 54.3% and 103.3% are not correct and shall be revised. |  |  | Notation was different, has been updated CES reply: Closed. Please check and update the document with pulsation dampenr data sheet.
| Please check the pressure again considering that allowable PEAK-PEAK shall be less than 7%. |  |  | updated CES reply: Closed.
| Please check these again considering ALLOWABLE PRESSURE DROP THROUGH SUPPRESSORS. |  |  | there were som things swapped, has been update corectly CES reply: Closed.
| All modification shall be shown cloudy with revision mark. |  |  | changes are marked yellow CES reply: Closed.