## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 26/Apr/2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER DETAIL DRAWING FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00125 | Doc. No.: BU-20-VD-303-ME-DWG-0079
|  | Transmittal Date: 26/Apr/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | General comment: Vendor is expected to check all document carefully and eliminate discrepancy between them. For example design temperature, design pressure and capacity of pulsation dampener are different in P&ID, data sheets and drawing. |  |  | Noted P&ID will be updated as soon as this drawing and datahseet are approved. CES reply (May.02,2022): It is not implemented yet. Unfortunately the data stated in document has discrepancy with compressor data sheet. Pulsation dampener data sheet, compressor data sheet, P&ID and dampener drawing shall be checked again.
2 | Position of each pulsation dampener shall be specified. For example inlet of stage 2. |  |  | The names are give in the template below CES reply (May.02,2022): Closed.
3 | 1.Please clarify why design pressure is different in each document: - in pulsation damper data sheet: 25 bara - in PID: 26 bara |  |  | it has been updated to the correct value. P&ID will be updated accordingly CES reply (May.02,2022): See the comments in document. As per pulsation dampener data sheet 26 barg shall apply.
4 | With reference to clause 7.9.3.2 of API 618 5th, Vd= 1.6x (Vs/r1/k). Therefor, discharge pulsation dampener capacity of first stage of compressor shall not be less than 105 Liter. |  |  | Please see reply on approved datasheet comment, which now has been approved. CES reply (May.02,2022): Closed.
5 | 1.Please clarify why design pressure is different in each document: - in pulsation damper data sheet: 25 bara - in PID: 26 bara |  |  | it has been updated to the correct value. P&ID will be updated accordingly CES reply (May.02,2022): See the comments in document. As per pulsation dampener data sheet 26 barg shall apply.
6 | 2.What does +80 mean? A specific value must be reported. |  |  | it has been updated to the correct value. CES reply (May.02,2022): Closed.
7 | Please check. 26 bara or 26 barg. |  |  | it has been updated to the correct value. CES reply (May.02,2022): See the comments in document. As per pulsation dampener data sheet 26 barg shall apply.
8 | With reference to clause 4.5 of BU-20-D-000-PR-SPC-101 (ESS FOR AMBIENT, SITE CONDITION & UTILITY DATA), design temperature shall be at least 85C. |  |  | it has been updated to the correct value. CES reply (May.02,2022): See the comments in document. Since TAHH (10155) is 140 C, design temperature shall not be less than 140 C.
9
10
11
12
13
14
15
16
17
18
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19
19