## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 02/May/2022 | Rev.: 00
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL STRENGHT CALCULATION FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00127 | Doc. No.: BU-20-VD-303-ME-CAL-0078
|  | Transmittal Date: 02/May/2022 | Doc Rev.: 00
Item | CHCE Comment |  |  | Vendor Clarification
1 | COMMENTS: 1- In order to check mechanical strength calculation, vendor shall submit native files of calculation including "PV ELITE" as minimum. 2- In mechanical calculation (In PV ELITE model), vendor shall consider and model "WIND & SEISMIC" data as per MR. 3- Strength calculation and also local stress calculation for supports of the vessels shall be submitted by vendor. Please be noted that calculation for supports is required in order to check the "strength of supports, supports pad, anchor bolts and also local stress" due to wind and seismic loads. |  |  | 1- Native files will not be provided as discussed during the KOM, 6.2 of KOM specifies that all documents like drawing and calculation, etc will be supplied in PDF format. KOM overules the TCL CES REPLY (May.09,2022): Closed. Only for instrument air compressor. 2- Wind and seismic for small vessels like this are not considered, since they are mountend inside the skid, normally wind and seismic calculation are only done when the vessel is mounted seperately. CES REPLY (May.09,2022) : Not accepted. Effect of wind and seismic for any pressure vessels (even if located inside of package) shall be considered in design of pressure vessels. 3- you asked to do it in PV-elite, support stress calculation cannot be done in PV-elite. also refer to point no 2. CES REPLY (May.09,2022) : Closed. But appropriate design of pulsation dampener is in vendor responsibility.
2