## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 16/Jun/2022 | Rev.:04
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER DETAIL DRAWING FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00150 | Doc. No.: BU-20-VD-303-ME-DWG-0079
|  | Transmittal Date: 16/Jun/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | Pulsation dampener calculation with PV ELITE native file shall be sent before next revision of pulsation dampener drawing. |  |  | PV-elite calculation has been submitted as PDF as per MOM of KOM CES reply (May.10,2022): Will be descussed in related document.
2 | 26 barg |  |  | is already mentioned CES reply (May.10,2022): See the latest comment in document.
2 | Shall be checked with P&ID. |  |  | P&ID has been updated CES reply (May.10,2022): Closed.
2 | Since TAHH (10155) is 140 C, design temperature shall not be less than 140 C. |  |  | P&ID has been updated CES reply (May.10,2022): Considering 2 C margin between operating temperature and design temperature is not enough and logical. Please consider at least 15 C margin between them.
2 | As per compressor data sheet discharge temperature is 81 C. |  |  | there is a typo in the datasheet CES reply (May.10,2022): Closed. We are waiting to receive revised data sheet.
2 | With reference to mechanical data sheet of pulsation dampener design pressure is 14.5 barg. |  |  | is already mentioned CES reply (May.10,2022): Closed.
2 | With reference to P&ID design temperature is 210 C |  |  | on the P&ID 170°C is mentioned CES reply (May.10,2022): Closed.
2 | 26 barg |  |  | is already mentioned CES reply (May.10,2022): See the latest comment in document.
2 | 26 barg |  |  | is already mentioned CES reply (May.10,2022): See the latest comment in document.
2
2 |  |  |  | all comments are updated in this revision CES reply (May.15,2022): It is not implemented yet. See the latest comments.
2
2 | Repetitive comment: Effect of wind and seismic load shall be considered in design of pulsation dampener. |  |  | as mentioned previously in E-mail, this is not required CES reply (Jun.08,2022): Regardless of size of pulsation dampeners and heat exchangers wind and seismic effect shall be considered in design of all equipment. It is clearly stated in material requisition, ASCE 7-16 shall be considered in design of all equipment and packages. As discussed during the meeting on 14th of June, we have submitted a warrantee letter for the wind and seismic loads. based on this please approve these drawings. CES reply (Jun.21,2022): Closed. Since AIRPACK guarantees both thermal and mechanical design of heat exchangers as well as mechanical design of pulsation dampeners, PV&HTIR native files may not be sent and seismic and wind effect may not be considered. AIRPACK, also, undertakes the full guarantee and responsibility of the aforementioned equipment as well as the whole package which means client does not bear any responsibility in document checking, and will not tolerate any malfunctions during operation of the package for any reason.
2 | 1.Discrepancy with PID |  |  | updated in latest rev. of P&ID CES reply (Jun.08,2022): Closed.
2 | Shall not be less than PSV set pressure. Design pressure shall be at least 26 bara. |  |  | updated CES reply (Jun.08,2022): Closed.
2
2 | Design temperature shall be checked with THH of discharge gas. |  |  | P&ID was already update TAHH is now 100°C CES reply (06.21,2022): Closed.
2 | With reference to mechanical data sheet of nitrogen compressor, operating temperature is 81 C. |  |  | Typo in the datasheet off the compressor, we will update in next revision. CES reply (06.21,2022): Closed.
2 | ~ |  |  | updated. CES reply (06.21,2022): Closed.
2 | revision |  |  | updated CES reply (06.21,2022): Closed.
2
2
2
2
2
2
2
2
2
2
2