## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 16/Jun/2022 | Rev.:04
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER DETAIL DRAWING FOR EMERGENCY INSTRUMENT AIR COMPRESSOR
|  | Transmittal No.: APCES-V-00150 | Doc. No.: BU-20-VD-303-ME-DWG-0080
|  | Transmittal Date: 16/Jun/2022 | Doc Rev.: 04
Item | CHCE Comment |  |  | Vendor Clarification
1 | Pulsation dampener calculation with PV ELITE native file shall be sent before next revision of pulsation dampener drawing. |  |  | PV-elite calculation has been submitted as PDF as per MOM of KOM CES reply (May.10,2022): Closed.
2 | 14.5 barg. |  |  | Noted is already mentioned CES reply (May.10,2022): See the latest comments.
2 | 26 barg |  |  | Noted is already mentioned CES reply (May.10,2022): See the latest comments.
2
2 |  |  |  | all comments are updated in this revision CES reply (May.15,2022): It is not implemented yet. Wind and seismic effect in design of pulsation dampener shall be considered by vendor.
2
2 | Repetitive comment: wind and seismic effect for design of equipment shall be considered by vendor. |  |  | as mentioned and explained in previous E-mail this is not required for these small vessels. CES reply (Jun.08,2022): Regardless of size of pulsation dampeners and heat exchangers wind and seismic effect shall be considered in design of all equipment. It is clearly stated in material requisition, ASCE 7-16 shall be considered in design of all equipment and packages. As discussed during the meeting on 14th of June, we have submitted a warrantee letter for the wind and seismic loads. based on this please approve these drawings. CES reply (Jun.21,2022): Closed. Since AIRPACK guarantees both thermal and mechanical design of heat exchangers as well as mechanical design of pulsation dampeners, PV&HTIR native files may not be sent and seismic and wind effect may not be considered. AIRPACK, also, undertakes the full guarantee and responsibility of the aforementioned equipment as well as the whole package which means client does not bear any responsibility in document checking, and will not tolerate any malfunctions during operation of the package for any reason.
2
2 | ~ |  |  | updated CES reply (Jun.21,2022): Closed.
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2