## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 16/Jun/2022 | Rev.: 02
|  | Comment Sheet Ref.No.: | Doc Description: After cooler mechanical strenght calculation
|  | Transmittal No.: APCES-V-00150 | Doc. No.: BU-20-VD-303-ME-CAL-0069
|  | Transmittal Date: 16/Jun/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | With reference to clause M8 of TCL PV ELITE native file shall be submitted. |  |  | It was never agreed to submit a Native file for the strength calculation, during KOM it was decided to only suply PDF file, please check the minutes CES reply (May.09,2022): Closed. Only for instrument air compressor.
2 | Wind and seismic (for seismic see clause 3.20.10 of requisition) effect shall be consider in design of heat exchanger. |  |  | as per requesition, it mentiones that it has to be considered for the package, not for separate items this will not be done. CES reply (May.12,2022): Your justification is not accepted. It shall be considered for all equipment. This item has been implemented by all compressor manufacturer (such as SIAD company)
3 | Repetitive comment: 1- Wind and seismic (as per ASCE 7-16 (see report in page 13 of requisition)) effect for design all pressure vessels (even if located inside of package) shall be considered by vendor. |  |  | As discussed during the meeting on 14th of June, we have submitted a warrantee letter for the wind and seismic loads. based on this please approve these drawings. CES reply (Jun.21,2022): Closed. Since AIRPACK guarantees both thermal and mechanical design of heat exchangers as well as mechanical design of pulsation dampeners, PV&HTIR native files may not be sent and seismic and wind effect may not be considered. AIRPACK, also, undertakes the full guarantee and responsibility of the aforementioned equipment as well as the whole package which means client does not bear any responsibility in document checking, and will not tolerate any malfunctions during operation of the package for any reason.