## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 23/Jun/2022 | Rev.: 01
|  | Comment Sheet Ref.No.: | Doc Description: PULSATION DAMPER MECHANICAL STRENGHT CALCULATION FOR NITROGEN GAS BOOSTER
|  | Transmittal No.: APCES-V-00153 | Doc. No.: BU-20-VD-303-ME-CAL-0026
|  | Transmittal Date: 23/Jun/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Repetitive comment: 1- Wind and seismic (as per ASCE 7-16 (see report in page 13 of requisition)) effect for design all pressure vessels (even if located inside of package) shall be considered by vendor. 2- As per clause M8 of nitrogen compressor TCL, native PV ELITE file shall be submitted by vendor (see enclosed TCL of nitrogen compressor). |  |  | 1) as per Teams meeting, this is no longer required due to warranty letter CES reply (Jun.26,2022): Closed. Since AIRPACK guarantees both thermal and mechanical design of heat exchangers as well as mechanical design of pulsation dampeners, PV&HTIR native files may not be sent and seismic and wind effect may not be considered. AIRPACK, also, undertakes the full guarantee and responsibility of the aforementioned equipment as well as the whole package which means client does not bear any responsibility in document checking, and will not tolerate any malfunctions during operation of the package for any reason. 2) sames a with the other one, this will not be supplied. CES reply (Jun.26,2022): Closed. Since AIRPACK guarantees both thermal and mechanical design of heat exchangers as well as mechanical design of pulsation dampeners, PV&HTIR native files may not be sent and seismic and wind effect may not be considered. AIRPACK, also, undertakes the full guarantee and responsibility of the aforementioned equipment as well as the whole package which means client does not bear any responsibility in document checking, and will not tolerate any malfunctions during operation of the package for any reason.
2