## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 25/Nov./2022 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: ALL EQUIPMENT NAME PLATE DRAWING
|  | Transmittal No.: APCES-V-00199 | Doc. No.: BU-20-VD-303-ME-DWG-0029
|  | Transmittal Date: 25/Nov/2022 | Doc Rev.: 01
Item | CHCE Comment |  |  | Vendor Clarification
1 | Agent name shall be deleted. |  |  | Updated CES reply (Dec.04,2022): Closed.
2 | Reciprocating compressor |  |  | Updated CES reply (Dec.04,2022): Closed.
3 | With reference to mechanical data sheet, discharge pressure of stage one is 14.5 barg. |  |  | Information on the P&ID must be followed. CES reply (Dec.04,2022): Closed.
4 | Unit shall be checked again. |  |  | Updated CES reply (Dec.04,2022): Closed.
5 | Considering PSV set pressure, design pressure shall be checked again. |  |  | Design pressure will be 26 bar (g) CES reply (Dec.04,2022): Closed.
6 | Please check the minimum design temperature. |  |  | Updated CES reply (Dec.04,2022): Closed.
7 | Please add Compressor rated speed to name plate. Please add compressor stroke. |  |  | Updated CES reply (Dec.04,2022): Closed.
8 | With reference to compressor data sheet, discharge temperature of stage 2 is 134 C. |  |  | The discharge temperature of stage 1 is 134 and the discharge temperature of stage 2 is 83. CES reply (Dec.04,2022): With reference to compressor data sheet, 81 C is correct.
9 | Please use same unit. |  |  | Updated CES reply (Dec.04,2022): Closed.
10 | Name plate of both compressor shall be same. Design temperature is missing for compressor 7080. |  |  | Updated CES reply (Dec.04,2022): Closed.
11 | With reference to general arrangement drawing of compressor 7080, total weight is 3500 kG. |  |  | Operational weight is 3200 KG CES reply (Dec.04,2022): Closed. GA drawing shall be revised in AB revision.
12 | Predicted discharge temperature as per mechanical data sheet shall be added. |  |  | Updated CES reply (Dec.04,2022): Closed.