## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 28/Dec/2022 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: ALL EQUIPMENT NAME PLATE DRAWING
|  | Transmittal No.: APCES-V-00205 | Doc. No.: BU-20-VD-303-ME-DWG-0029
|  | Transmittal Date: 28/Dec/2022 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification
1 | Agent name shall be deleted. |  |  | Updated CES reply (Dec.04,2022): Closed.
2 | Reciprocating compressor |  |  | Updated CES reply (Dec.04,2022): Closed.
3 | With reference to mechanical data sheet, discharge pressure of stage one is 14.5 barg. |  |  | Information on the P&ID must be followed. CES reply (Dec.04,2022): Closed.
4 | Unit shall be checked again. |  |  | Updated CES reply (Dec.04,2022): Closed.
5 | Considering PSV set pressure, design pressure shall be checked again. |  |  | Design pressure will be 26 bar (g) CES reply (Dec.04,2022): Closed.
6 | Please check the minimum design temperature. |  |  | Updated CES reply (Dec.04,2022): Closed.
7 | Please add Compressor rated speed to name plate. Please add compressor stroke. |  |  | Updated CES reply (Dec.04,2022): Closed.
8 | With reference to compressor data sheet, discharge temperature of stage 2 is 134 C. |  |  | The discharge temperature of stage 1 is 134 and the discharge temperature of stage 2 is 83. CES reply (Dec.04,2022): With reference to compressor data sheet, 81 C is correct.
9 | Please use same unit. |  |  | Updated CES reply (Dec.04,2022): Closed.
10 | Name plate of both compressor shall be same. Design temperature is missing for compressor 7080. |  |  | Updated CES reply (Dec.04,2022): Closed.
11 | With reference to general arrangement drawing of compressor 7080, total weight is 3500 kG. |  |  | Operational weight is 3200 KG CES reply (Dec.04,2022): Closed. GA drawing shall be revised in AB revision.
12 | Predicted discharge temperature as per mechanical data sheet shall be added. |  |  | Updated CES reply (Dec.04,2022): Closed.
Item | CHCE Comment |  |  | Vendor Clarification
1 | Repetitive comment: Name plate of following equipment shall be added to this document: 1- Electrical motors 2- Name plate for each cylinder as per clause 6.16.5 of API 618 5th edition. |  |  | As per manufacturer standard, Electrical motors nameplate is not included in the document. Nameplate for each cylinder is not possible at the manufacturer. CES reply (Dec.19,2022): Closed.
2 | There is no need to add purchase order no to name plate. |  |  | Updated, purchase order number is deleted from the nameplate CES reply (Dec.19,2022): Closed.
3 | Compressor design pressure is 26bara. |  |  | Noted, Updated in the next revision CES reply (Dec.19,2022): Closed.
4 | 0 / 210 |  |  | Noted, Updated in the next revision CES reply (Dec.19,2022): Closed.
5 | With reference to compressor data sheet, 81C is correct. |  |  | Noted, Updated in the next revision CES reply (Dec.19,2022): Closed.
6 | There is no need to add purchase order no to name plate. |  |  | Updated, purchase order number is deleted from the nameplate CES reply (Dec.19,2022): Closed.
7 | Discharge pressure |  |  | Noted, Updated in the next revision CES reply (Dec.19,2022): Closed.
8 | Unit in both name plate shall be same. |  |  | Noted, Updated in the next revision CES reply (Dec.19,2022): Closed.
Item | CHCE Comment |  |  | Vendor Clarification
1 | Please check the design pressure again. With reference to compressor data sheet adiabatic discharge temperature is 180C and also design temperature in shell side of heat exchanger is 210 C. It seems that 210 C is correct. Also, HH set point of TT is 195 C. |  |  | updated acordingly in the next revision. CES reply (Jan.01,2023): Closed.
2