## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 14/Jul/2023 | Rev.:01
|  | Comment Sheet Ref.No.: | Doc Description: commissioning and start-up spares
|  | Transmittal No.: APCES-V-00218 | Doc. No.: BU-20-VD-303-ME-LST-0055
|  | Transmittal Date: 14-Jul/2023 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | Compressor 1002 - Oil wiper packing inner parts (CC0806) are missing. - Packing inner part is missing. Compressor 7080 - Packing inner part is missing. |  |  | not required, this is only commissioning and start-up spares CES reply (Jul.29,2023): Its required as per your contract. With reference to AIRPACK technical offer, all items mentioned in comment 1 are in AIRPACK cope of work supply.
2 | Compressor is two stage and each stage have 2 valves. 4 for suction and discharge is correct. |  |  | noted and updated CES reply (Jul.29,2023): Closed.
3 | Compressor cross sectional drawing shall be reported |  |  | noted and updated CES reply (Jul.29,2023): Closed.
4 | Stage 2 is missing. |  |  | noted and updated CES reply (Jul.29,2023): Closed.
5 | Row 15 shall be fill in same as row 14. |  |  | noted and updated CES reply (Jul.29,2023): Closed.
6 | There is no need to write anything such as 0 in this column. |  |  | noted and updated CES reply (Jul.29,2023): Closed.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56