## COMMENT REPLY SHEET
|  | Comment Reply Sheet |  |  | BUSHEHR PETROCHEMICAL COMPANY
Con. No.:
[5 empty] | Issue Date: 14/Jul/2023 | Rev.:02
|  | Comment Sheet Ref.No.: | Doc Description: Two years spare parts list
|  | Transmittal No.: APCES-V-00218 | Doc. No.: BU-20-VD-303-ME-LST-0054
|  | Transmittal Date: 14/Jul/2023 | Doc Rev.: 02
Item | CHCE Comment |  |  | Vendor Clarification |  |  | CES Reply | Vendor Clarification
1 | All items mentioned in attached file shall be supplied by AIRPACK for commissioning spare part list. |  |  | noted and completed CES reply (Jul.29,2023): Please see the comment given in document.
2 | Model number of VT, PT, TT, and FT shall be specified. |  |  | noted and completed CES reply (Jul.29,2023): Manufacturer model number as per instrument data sheet shall be written.
3 | DE or NDE shall be specified. Also, code of bearing as per motor data sheet shall be written. |  |  | noted and completed CES reply (Jul.29,2023): Closed.
4 | Pulsation dampeners. |  |  | noted and completed CES reply (Jul.29,2023): Closed.
5 | Relay, barrier and etc. shall be written in individual row. |  |  | noted and completed CES reply (Jul.29,2023): Closed. Please see the document.
614:23B1614:2214:24B1614:2214:261414:51 | Exact quantity shall be written not the percent. |  |  | noted and completed CES reply (Jul.29,2023): Closed.
7 | - Size of all o-ring and gasket shall be specified. - Some items are missing. For example fan of electrical motor, tube of heat exchanger and etc. See general comment in page 1.I16 |  |  | will not be included according to TQ that was received on 20-02-2023 CES reply (Jul.29,2023): Closed, for material of compressor part. However there are some items wich are missing. Please see the document.
8 | Exact material shall be specified. |  |  | will not be included according to TQ that was received on 20-02-2023 CES reply (Jul.29,2023): Closed
9 | Project document for example instrument data sheet or etc. shall be written in reference document column. |  |  | noted and completed CES reply (Jul.29,2023): Please see the comment given in document.
10 | Piston ring and guide ring shall be written in individual row. |  |  | noted and completed CES reply (Jul.29,2023): Closed
11 | - Spar part of each compressor shall be specified in individual page. - Electrical motor, instrumentation, mechanical items, PLC and etc. shall be specified in individual columns of each compressor page. Please see the sample SPLIR form. |  |  | noted and completed CES reply (Jul.29,2023): Please see the explanation given in page there.
12 | Manner of filling SPLIR format shall be same as attached file. |  |  | see above CES reply (Jul.29,2023): Please see the sample file again.
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56