## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Index of Instruction and Operating Manual | L03-RE037-ME-INX-002 23249-20
Item no. | Page | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | 1 | 01 | Closed | Electrical load list | Not part of the VDS, will not be included | NOTED
2 |  |  | Closed | Standards:IEC;DIN/VDE;ISO | Will not be included, this is IOM | NOTED
3 |  |  | Closed | Main Motor Data sheet | Will be included | NOTED
4 |  |  | Closed | HAZOP and SIL Studies and Report | Not part of the PO, will not be included | NOTED
5 |  |  | Closed | Total Weights | This can be found in the Data book section F-1 | NOTED
6 |  |  | Open |  |  | Please consider now comment in doc: Do you issue another document for nstallation, commissioning and operating Manual? If not, please include them in this document. | This is the same. Installation, commissioning and operating are all included in this document.
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20