## Resolution Sheet
PROJECT:
COMMENT RESOLUTION SHEET FOR: |  |  |  |  | DOC TITLE: | DOC No:
[5 empty] | Valve datasheets | L03-RE037-IN-DSH-003 (23249-27)
Item no. | Reference | Revision | Status | Client Comments | AirPack's Reply #1 | Client Reply #1 | AirPack's Reply #2 | Client Reply #2
1 | Page 3 | Rev 00 |  | All tag numbers shall be start with two digit 68 We are in unit 68 (not 60) | Updated
2 | Page 4 | Rev 00 |  | Please follow our datasheet | Updated to instrument air. Please clarify what this comment refers to.
3 | Page 4 | Rev 00 |  | Shall be Exia IICT4 | The solenoid is Ex'd' according to the offer and the previous project.
4
5
6
7 | [8 empty] | Open
8 | [8 empty] | Closed
9
10
11
12
13
14
15
16
17
18
19
20